## Intro and Table of Contents
DSRIP Implementation Plan
Introduction to this prototype: This is the first installment of the DSRIP Implementation Plan Prototype. This document contains sections of a hypothetical 'prototype' implementation plan, written on behalf of Forestland PPS. This first installment contains the following organizational sections: Workforce Strategy; Governance; and Financial Sustainability. It also contains the General Project Implementation section and four example projects: 2.a.i, 2.a.iv, 3.a.i, and 4.a.iii.
Table of Contents
Organizational Sections |  | Project Implementation Plan Sections
General project implementation section
|  | Domain 2 |  | Domain 3 |  | Domain 4
Workforce Strategy | Budget | 2.a.i | 2.b.vi | 3.a.i | 3.d.ii | 4.a.i
Governance | Funds Flow | 2.a.ii | 2.b.vii | 3.a.ii | 3.d.iii | 4.a.ii
Financial Sustainability |  | 2.a.iii | 2.b.viii | 3.a.iii | 3.e.i (Model 1) | 4.a.iii
Cultural Competency and Health Literacy |  | 2.a.iv | 2.b.ix | 3.a.iv | 3.e.i (Model 2) | 4.b.i
IT Systems & Processes |  | 2.a.v | 2.c.i | 3.a.v | 3.f.i (Model 1) | 4.b.ii
Performance Reporting |  | 2.b.i | 2.c.ii | 3.b.i | 3.f.i (Model 2) | 4.c.i
Practitioner Engagement |  | 2.b.ii | 2.d.i | 3.b.ii | 3.f.i (Model 3) | 4.c.ii
Population Health Management |  | 2.b.iii |  | 3.c.i | 3.g.i | 4.c.iii
Clinical Integration |  | 2.b.iv |  | 3.c.ii | 3.g.ii | 4.c.iv
|  | 2.b.v |  | 3.d.i | 3.h.i | 4.d.i

## Instructions
Instructions
Note: the instructions on this tab relate to the template, rather than the prototype. Please see the "Before you begin.." tab for more notes on the prototype.
You must complete all of the organizational sections of the implementation plan and all of the project plan applications for the particular projects you are undertaking.
Part 1: The Organizational Implementation Plan Sections
There are a total of eleven organizational sections: Governance, Workforce, Financial Sustainability, Cultural Competency, IT Systems and Processes, Population Health Management, Clinical Integration, Performance Reporting, Practitioner Engagement, Budget and Funds Flow. You must complete all of these sections. In most of these sections there are a number of specific milestones. In order for this template to be considered complete, you must enter the demonstration year and quarter by which you will achieve each milestone and set out the key sub steps that you will undertake in order to reach this milestone. The template also sets out, for each milestone, what supporting evidence you will be required to provide to the Independent Assessor in order to demonstrate: (a) that you have achieved that milestone; and (b) on an ongoing basis through the quarterly reporting process regarding that particular milestone. There are several milestones/questions which are required for the first quarterly report, but for which the dates are not yet defined. Within your first quarterly report, you must enter, at minimum, an estimate to show that work is under way. A more detailed approach will be announced as soon as possible.
Part 2: The Project Implementation Plan Sections
The 'General Project Implementation' tab contains a number of headings to which you must respond. These headings apply across all of your chosen projects. You therefore only need to fill this tab out once. You should then complete a separate project implementation plan for each of your chosen DSRIP projects. Within each Domain 2 and 3 project tab, you will find a Project Implementation Speed table. This table requires you to provide a quarter-by-quarter breakdown of the target you set for Project Speed of Implementation in your project plan application for each project. Having set your quarterly targets for project implementation speed in this template, you will then be required to report your progress through the quarterly reports. Note: the Project Implementation Speed table for Project 2.a.i is structured differently to the tables for all other projects. You will also find a Patient Engagement Speed table within each Domain 2 and 3 project tab (except Project 2.a.i). This table requires you to provide a quarter-by-quarter breakdown of the target you set for Patient Engagement Speed in your project plan application for each project. These quarterly forecasts for Patient Engagement Speed should match the counting methodology used in the Patient Engagement Speed Table for your project plan application for the corresponding project. The only difference in this Implementation Plan is that the values entered will be on a quarterly basis instead of a semi-annual basis. The counting methodology remains the same. For more detail on the counting methodology, please consult the DSRIP website. In summary, the counting methodology will be either: -- A count of patients that meet the criteria for 'actively engaged' over a 1-year measurement period. Duplicate counts of patients are allowed, provided that they meet the criteria more than once. The count is not additive across DSRIP years (projects 2.b.iv, 2.b.v, 2.b.vi and 3.a.ii); or -- A count of patients that meet the criteria for 'actively engaged' over a 1-year measurement period. Duplicate counts of patients are not allowed. The count is not additive across DSRIP years (projects 2.a.ii, 2.a.iii, 2.a.iv, 2.a.v, 2.b.i, 2.b.ii, 2.b.iii, 2.b.vii, 2.b.viii, 2.b.ix, 2.c.i, 2.c.ii, 2.d.i, 3.a.i, 3.a.iii, 3.a.iv, 3.a.v, 3.b.i, 3.b.ii, 3.c.i, 3.c.ii, 3.d.i, 3.d.ii, 3.d.iii, 3.e.i, 3.f.i, 3.g.i, 3.g.ii and 3.h.i)
NOTES ON THE PROJECT IMPLEMENTATION PLANS: - The quarterly speed of implementation targets that you set in this template must align with the overall targets that you committed to in your project plan application for each project. - For Domain 2 & 3 projects, there will be specific Achievement Values associated with PPSs meeting: (a) their quarterly project implementation speed targets; and (b) their quarterly patient engagement speed targets. More detail on the assessment of Achievement Values and how they drive Domain 1 Process Payments will be forthcoming shortly in an 'AV Policies & Procedures Guide'. - A more detailed version of the Project Implementation Speed table than the one included in this template will be published in Spring/Summer 2015 for PPSs to complete. The due date for this table, as well as the due dates for any other elements of the implementation plan not required by April 1, will be published shortly. - PPSs will ultimately be required to identify all of the providers committed to each project. This will not be required for the April 1st submission of this template, but will ultimately be required for the quarterly reporting process using the MAPP tool. Throughout the 5 years of the DSRIP program, PPSs will be able to swap providers into and out of the lists of providers committed to particular projects. However, they will still be held accountable to the overall numbers they commit to in their project speed and scale of implementation tables.

## Before You Begin...
Before you begin…
A note on the prototype: This prototype does not contain detailed speed of implementation commitments for Forestland PPS (i.e. the patient speed of engagement table and the project speed of implementation table). The ramp up of speed of implementation is so specific to each PPS that including a hypothetical example would not have provided any useful guidance. While this prototype is a hypothetical example, the target completion dates within it are all within a reasonable timeframe for completion of those milestones. Ultimately, it will be the role of the Independent Assessor to make a judgment about what constitutes an acceptable timeframe for completion of a given milestone for each PPS. As described below, PPSs are able to add milestones into their implementation plans in addition to those milestones prescribed by the template. In this hypothetical example, Forestland PPS has added some additional milestones into some sections (notably Financial Sustainability). Please note: these additional milestones are part of the prototype and will not be included in the template; the milestones prescribed in the template are the only ones that PPSs must set target completion dates for in their April 1st implementation plans. You should consult the template for clarity on which milestones are mandatory.
Background: The Implementation Plan as the basis for the Quarterly Reports Each quarter throughout the DSRIP program, PPSs must submit a quarterly report to the Independent Assessor. This quarterly reporting process will ultimately be automated via the MAPP tool. The submission of a complete quarterly report will drive one of the Achievement Values that drive Domain 1 process payments. The link between the different sections of the implementation plan & quarterly reports and Domain 1 process payments will be articulated in more detail in the 'AV Policies & Procedures' guide, which will be released shortly. This implementation plan will create a baseline against which the quarterly reports measure progress, although there are some sections for which that baseline will be created at a later date - for example, PPSs will not be expected to provide refined workforce transformation numbers (new hires, retraining, redeployment etc.) in this document. The exact timeline for when these refined workforce transformation numbers will be required - along with details of all the elements of this implementation plan that will be required at a later date - will be published shortly. You will see that the organizational sections of this implementation plan include specific milestones. In order for the implementation plan to be considered complete, PPSs must set dates for when they will achieve these milestones and must set out the steps they will take towards that milestone. For each of the milestones, this document also describes the specific supporting documentation or evidence that PPSs must submit to demonstrate they have achieved the milestone, as well as the evidence they will be required to submit on an ongoing basis in the quarterly reports.
The implementation plan milestones The table below is an example of the milestone tables that you will see throughout this template.
The Milestone: PPSs must enter a target completion date against all specified milestones. You will then use the quarterly reporting process to update the Independent Assessor on your progress against this target date. Should you need to revise this target date, you will be able to do so, without compromising any achievement values associated with that milestone, as long as you provide sufficient explanation to the Independent Assessor explaining why your projected timeline has changed and what your plans are for addressing this. The milestones prescribed in this template are not necessarily listed in sequential order; in the example table below, for example, you could set a target date for 'Establish a clinical governance structure...' that is later than your target completion date for 'Finalize bylaws and policies'. You can also add additional milestones should you wish. Whether you add additional milestones or not, you must, at a minimum, set target completion dates for all of the milestones prescribed in this document.
Target Completion Date: You must fill in this column using the drop down list, indicating in which year and quarter you will complete the milestone or step.
Supporting Documentation: This column describes the evidence that PPSs will need to submit, to the Independent Assessor's satisfaction, in order to demonstrate that the milestone in question has been achieved. Where relevant, we have set out the key elements that these pieces of supporting documentation will need to cover. More detail will be forthcoming in the 'AV Policies and Procedures' guide.
Step 1, Step 2, Step 3 etc.: These rows are where you should set out the key steps you will take in working towards the milestone above, as well as your target completion dates for these steps. You will not be asked to provide supporting documentation to demonstrate that you have undertaken these steps. These steps are intended to give DOH and the Independent Assessor more insight into the planning and implementation process that each PPS is undertaking. You should add more rows into the table in order to set out all of your key steps.
| Governance structure updates | Target Completion Date | Supporting Documentation
| Milestone: Establish a clinical governance structure, including clinical quality committees for each DSRIP project |  | Clinical Quality Committee charter and committee structure chart Subsequent quarterly reports will require minutes of clinical quality committee meetings to be submitted.
Step 1…
Step 2…
| Milestone: Finalize bylaws and policies or Committee Guidelines where applicable |  | Upload of bylaws and policies document or committee guidelines. Subsequent quarterly reports will require PPSs to articulate any updates that have been made to their bylaws, policies or committee guidelines.
Step 1…
Step 2…
A note on printing this document:
We have optimized the settings of this document for printing as far as possible but these settings may change depending on your own default settings. If you would like to print this document, you can take the following steps to make your document print-friendly (if it is not already configured as such): 1. Select all sheets in the document (select the first tab, scroll to the last tab, hold down 'Shift' and select the last tab) 2. Go to File > Print Preview 3. Within the Print Settings: (1) select 'Print Entire Workbook'; (2) set Page Orientation to Landscape; and (3) set your Scaling to 'Fit All Columns on One Page' if printing to paper, or 'Fit Sheet on One Page' if printing to PDF.

## Workforce Strategy
Workforce Strategy
Key Steps and Measurable Milestones
Domain 1 Process Measures - this section is linked to a specific achievement value in the implementation plan & quarterly report process
i. Workforce Strategy Budget Updates
[Note: You do not need to provide revised workforce budget numbers for the April 1 submission. A revised, finalized budget will be required (in the format set out below) before the end of DY 1. A detailed timeline of when this will be required will be published shortly. Once you have provided these revised workforce budget numbers, the quarterly reporting process will require you to provide updates on your actual spend compared to this budget.]
Funding Type |  | DY1 Spend | DY2 Spend | DY3 Spend | DY4 Spend | DY5 Spend | Total Spend
Retraining
Redeployment
New Hires
Other
ii. Workforce Impact Analysis and Updates
[Note: You do not need to provide revised workforce impact numbers for the April 1 submission. A revised, finalized set of workforce impact numbers (in the format set out below) will be required before the end of DY 1. A detailed timeline of when this will be required will be published shortly. Once you have provided these revised workforce impact numbers, the quarterly reporting process will require you to provide updates on (and evidence of) your redeployment, retraining and new hires compared to these forecasts.]
Workforce Implication |  |  | Percent of Employees Impacted (%) |  |  |  | Number of Employees Impacted
Redeploy
Retrain
New Hire
Placement Impact |  |  | Percent of Retrained Employees Impacted (%) |  |  |  | Number of Retrained Employees Impacted
Full Placement
Partial Placement
No Placement
iii. New Hire Employment Analysis and Updates
[Note: You do not need to provide revised new hire employment analysis numbers for the April 1 submission. A revised, finalized set of numbers will be required before the end of DY 1. A detailed timeline of when this information will be required will be published shortly. Once you have provided these revised New Hire numbers, the quarterly reporting process will require you to provide updates on (and evidence of) your new hires compared to these forecasts.]
Staff Type |  |  |  | New Hires Net Change
[staff type 1]
[staff type 2]
[staff type 3]
[staff type 4]
[…]
[…]
Key Issues - this section is not linked to the specific workforce achievement value
Workforce Impact Analysis | [5 empty] | Target Completion Date |  | Supporting Documentation
Milestone: Define target workforce state (in line with DSRIP program's goals) | [5 empty] | DY1, Q3 |  | Finalized PPS target workforce state, signed off by PPS workforce governance body. Subsequent quarterly reports will require an update on the implementation of your workforce transition roadmap, including any change to your target state.
Step 1: Establish Workforce Project Team (including workforce committee, project leads, union representation, and other appropriate subject matter experts and key stakeholders) tasked with implementing and executing workforce related activities as laid out in the Implementation Plan | [5 empty] | DY1, Q2
Step 2: Identify and map out the specific requirements of each DSRIP project and the new services each of the projects will require or deliver (through a series of workshops, interviews and surveys with key stakeholders and project leads) | [5 empty] | DY1, Q2
Step 3: Perform an Organizational Impact Assessment to determine the project-by-project impact on the Forestland PPS workforce (degree and magnitude of impacts by role / provider organization, key roles and responsibility changes, skills/competency changes, impact to staffing patterns, impact to caseloads, etc.) | [5 empty] | DY1, Q2
Step 4: Determine, on a project-by-project basis, if the impact to a particular role will be low, medium, or high | [5 empty] | DY1, Q2
Step 5: Perform a Future State Staffing Strategy Analysis that consolidates the project-by-project analysis in order to develop a comprehensive view of the areas within the PPS that will need more, less, or different resources to support the DSRIP projects | [5 empty] | DY1, Q3
Step 6: Perform a Future State Workforce Needs Assessment to capture detailed information on the competencies and responsibilities of the roles required per project | [5 empty] | DY1, Q3
Step 7: Based on data analyzed from Organizational Impact Assessment, Future State Staffing Strategy Analysis, and Future State Workforce Needs Assessment (e.g. what roles will be significantly impacted, what changes to the workforce will be needed), define the future state workforce that is required for DSRIP projects to succeed | [5 empty] | DY1, Q3
Milestone: Create a workforce transition roadmap for achieving your defined target workforce state. | [5 empty] | DY1, Q4 |  | Completed workforce transition roadmap, signed off by PPS workforce governance body. Subsequent quarterly reports will require an update on the implementation of your workforce transition roadmap.
Step 1: Develop governance/decision-making model that defines how and by whom any decisions around resource availability, allocation, training, redeployment and hiring will be made and signed off | [5 empty] | DY1, Q2
Step 2: Based on the vision of the Future State Workforce (defined in milestone above), develop consolidated map of all specific workforce changes required to the workforce; define timeline of when these changes will need to take place and what the dependencies are (for all training, redeployment and hiring in line with project timeline and needs) | [5 empty] | DY1, Q3
Step 3: Workforce governing body signs off on workforce transition roadmap (including timeline for the transition of the workforce from the current state to the future state) | [5 empty] | DY1, Q4
Milestone: Perform detailed gap analysis between current state assessment of workforce and projected future state | [5 empty] | DY1, Q4 |  | Current state assessment report & gap analysis, signed off by PPS workforce governance body. Subsequent quarterly reports will require an update on the implementation of your workforce transition roadmap.
Step 1: Perform current state assessment of staff availability and capabilities across the PPS and member organizations, identifying: - Staff who could fill future state roles through up-skilling and training; - Staff who could potentially be redeployed directly into future state roles (utilizing a redeployment needs assessment) | [5 empty] | DY1, Q2
Step 2: Map current state analysis against future state workforce (defined in milestone above) to identify new hire needs | [5 empty] | DY1, Q3
Step 3: Perform workforce budget analysis to established a revised WF budget for the projects over the duration of the DSRIP project | [5 empty] | DY1, Q3
Step 4: Update future state roadmap based on detailed gap analysis to articulate how (e.g. retraining, redeployment) and when (e.g. timing of redeployments) the transition of the workforce from the current state to the future state will occur | [5 empty] | DY1, Q4
Milestone: Produce a compensation and benefit analysis, covering impacts on both retrained and redeployed staff, as well as new hires, particularly focusing on full and partial placements. | [5 empty] | DY1, Q3 |  | Compensation and benefit analysis report, signed off by PPS workforce governance body. Subsequent quarterly reports will require an update on the implementation of your workforce transition roadmap, including updates on compensation and benefits.
Step 1: Utilizing the current state analysis performed in Milestone #3, identify the origin and destination of staff that are being redeployed to understand changes to impact jobs and member facilities | [5 empty] | DY1, Q2
Step 2: Work with HR to gather compensation and benefits information for existing roles that will potentially be redeployed | [5 empty] | DY1, Q2
Step 3: Assess changes to compensation and benefits, comparing current and future state compensation and benefits for impacted staff, taking into account job role, function, and location | [5 empty] | DY1, Q3
Step 4: Develop and incorporate policies for impacted staff who face partial placement, as well as those staff who refuse retraining or redeployment | [5 empty] | DY1, Q3
Step 5: Work with HR to determine specific impacts to partial placement staff and potential contingencies. Include labor groups in discussions | [5 empty] | DY1, Q3
Step 6: Finalize compensation and benefit analysis | [5 empty] | DY1, Q3
Milestone: Develop training strategy | [5 empty] | DY1, Q4 |  | Finalized training strategy, signed off by PPS workforce governance body. Quarterly reports will require evidence of up-take of training programs, including both individual training and training for new, multi-disciplinary teams. PPSs will need to provide: a description of training programs delivered and participant-level data, including training outcomes.
Step 1: Define current state training needs (through surveys and stakeholder interviews), including the specific skills and certifications that staff will require training on | [5 empty] | DY1, Q3
Step 2: Perform a Skills Assessment to understand existing capability for staff that will need to be retrained and document future state capability and skills needs for impacted staff | [5 empty] | DY1, Q3
Step 3: Finalize Training Strategy, including goals, objectives and guiding principles for the detailed training plan; confirm process and approach to training (e.g. voluntary vs. mandatory etc.) | [5 empty] | DY1, Q3
Step 4: Develop mechanism to measure training effectiveness in relation to established goals once strategy and plan are implemented | [5 empty] | DY1, Q3
Step 5: Finalize detailed Training Plan (based on Training Strategy), including, methods, channels and key messages required for training based on project needs. This includes consideration of geography, language, level of education, training tools, and methods of delivery | [5 empty] | DY1, Q4
Major Risks to Implementation & Risk Mitigation Strategies
Please describe the key challenges and risks that you foresee in achieving the milestones set out above, including potential impacts on specific projects and any risks that will undermine your ability to achieve outcome measure targets.
The key risks we have identified that could impact our ability to meet our baseline process measures in the future are: 1. Competition from the overlapping PPSs in the Greater Forestland area over high-demand positions – in particular, we have identified the [care navigator] role as one for which there is likely to be strong competition, as existing numbers of these staff are low in Greater Forestland and both the Forestland PPS and our neighboring PPS have identified this role as one of the pillars of the successful delivery of Project 2.a.i. We will collaborate with neighboring PPSs in our region and strive for equitable access among PPSs for staff hiring high-demand staff. Regular discussions will take place with the goal of ensuring the future state workforce needs of both PPSs are met. 2. Difficulty recruiting to providers in the Forestland PPS network, particularly for relatively low-paid roles, in light of the cost of living in Forestland, compared to other PPSs in the State that will also be recruiting for the same positions. To mitigate this risk, we will employ a strategy that looks beyond our immediate region for recruiting, and we will also build relationships with local education institutions, including the Greater Forestland Community College, to build a pipeline for high-need positions. 3. The possibility of DSRIP funding being lower than expected (due to variations in achievement values and associated process payments). We expect our workforce strategy to have a relatively high proportion of new hires (as opposed to redeployment / retraining), which leads to an expensive workforce transformation. As such, variations in DSRIP revenues present a significant risk. Should this take place, this PPS will return to core analyses to determine the best and more cost-effective contingency strategies that still allow major DSRIP goals to be achieved with available workforce. 4. A lot of requirements and projects, including 2.a.i., depend on the successful implementation of an electronic health records system, as well as the necessary training and change management and engagement support to ensure that impacted staff are ready, willing, and able to succeed with the new system. In order to execute the activities to support these endeavors in a timely and effective manner, Forestland PPS has begun contract discussions with DEF Workforce Consulting to provide technical assistance. We will institute strict project management and reporting protocols to ensure that we remain on track and on schedule with regard to getting our people, processes, and technology ready for success in the DSRIP future. 5. Forestland PPS may have difficulty obtaining buy-in and support from frontline workers and key stakeholders, which in turn could impact DSRIP project success. To mitigate this risk, it will be important for our PPS to include union representation in all committee structures as a means to gain worker support at all levels. A comprehensive change management strategy will also support this effort. 6. Forestland PPS has identified 5 large providers within its network that are also shared with as many as two neighboring PPSs, leading to some complexity in provider workforce counts. To mitigate the risk of overlap, the PPSs’ workforce teams have coordinated and will continue to coordinate their counts to ensure no double-counting of staff occurs in cases of shared providers.
Major Dependencies on Other Workstreams
Please describe the major interdependencies between your workforce transformation plans and other workstreams (e.g. cultural competency, clinical integration, financial sustainability, etc.)
A number of interdependencies exist between our workforce transformation plans and other organizational workstreams. First, given the significance of the workforce budget and the importance of directing funds to the providers in our network to support their training and redeployment needs, the connection between our PPS workforce transformation team and the Forestland PPS Finance Function is crucial. To that end, the Finance Function has a member of the workforce transformation team embedded within it. There is also a relationship between the training components of our workforce transformation plans and our cultural competency strategy. As well as the clinical and technical training that will be required for many impacted staff members, training linked to the cultural competency and health literacy strategy will be needed so that key staff members, including doctors, nurses, and patient navigators, are able to communicate in an effective way with our entire patient population, and so that they can understand the challenges related to poor health literacy. To this end, we will develop the training elements of our cultural competency strategy in tandem with our overarching training strategy. Further, workforce is closely tied to clinical integration, as much of the retraining of the workforce will focus on creating more integrated multi-disciplinary teams that cross organizational boundaries. As well as retraining, redeployment will be critical in ensuring that the right staff are placed in the right location to support better clinical integration and the success of projects such as 3.a.i and 2.a.i.
Roles and Responsibilities
Please list the key people/organizations responsible for this organizational workstream and describe what their responsibilities involve. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Role |  |  |  | Name of person / organization (if known at this stage) |  | Key deliverables / responsibilities
| Workforce IP Project Lead |  |  |  | Walter Orville |  | Dedicated Project Manager accountable for development of IP and execution of all workforce-related activities
| Workforce Committee |  |  |  | Robert Kline, Felicia Oppenheim, Richard C. Eisenberg |  | A group of cross-functional resources (e.g. WF PM, HR, DSRIP lead, Union representative, etc.) responsible for overall direction, guidance and decisions related to the workforce transformation agenda
| WF Training Vendor |  |  |  | ABC Training Group |  | A training vendor that can either support the execution of WF-related activities or provide training modules and/or certification training to support workforce re-training needs.
| Labor Representation |  |  |  | ABC Labor Group |  | Labor group(s) that can provide insights and expertise into likely workforce impacts, staffing models, and key job categories that will require retraining, redeployment, or hiring
| Workforce Consultant |  |  |  | DEF Workforce Consulting |  | Consulting firm responsible for the coordination and execution of workforce activities and analyses, reporting directly to the WF Project Manager
| Workforce Project Team |  |  |  | - |  | A group of PPS individuals responsible for executing or supporting the execution of key portions of the Implementation Plan activities
Key Stakeholders
Please identify the key stakeholders involved in your workforce transformation plans, both within and outside the PPS. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Key stakeholders |  |  |  | Role in relation to this organizational workstream |  | Key deliverables / responsibilities
Internal stakeholders
| Jay Sunny, Helga Berger |  |  |  | HR Leads of Forestland PPS |  | Support data collection of compensation and benefit information; current state workforce information and potential hiring needs
| Eva Line, Vaughn B. Eyck |  |  |  | Training Leads of Forestland PPS |  | Provide oversight and input to development of training needs assessment, and subsequent training strategy and plan
| Ricky King, Bobby Mud |  |  |  | Leads of larger PPS member organizations |  | Provide insights and information related sources and destinations of redeployed staff by project
| Jordan Softwood |  |  |  | Lead at large PPS member impacted by DSRIP projects |  | Provide data and information for current state assessment and future state workforce needs
External stakeholders
| ABC Labor Union |  |  |  | Labor/Union Representation |  | Expertise and input around job impacts resulting from DSRIP projects
| ABC Training Group |  |  |  | Training Vendor |  | Technical training curriculum development; recruiting support
| DEF Workforce Consulting |  |  |  | Workforce Vendor |  | Coordination and execution of workforce activities and analyses
IT Expectations
Please describe how the development of shared IT infrastructure across the PPS will support your plans for workforce transformation.
The relationship between IT and Workforce is an important one, and alignment between these two workstreams at Forestland PPS will be critical to DSRIP success. First, once our training strategy and plan are implemented, we will rely on IT platforms significantly to track training progress (e.g. tracking who’s been trained, the subject matter of the training, when the training took place, certification levels, etc.). This will require a cross-member organization learning management system (LMS) capability. Second, as Forestland PPS begins to execute the workforce transition roadmap, we will rely on IT capabilities to track staff movement and changes across the PPS (e.g. redeployed staff, net new hires). Forestland PPS will need a central IT system that is capable of tracking workforce changes, and is also capable of gathering data and information related to workforce changes in a seamless and timely fashion. Along the same lines, this system will also be necessary when the time comes to report workforce process measures on quarterly progress reports, as these figures (number and percentages of redeployed/retrained/hired staff, workforce budget) will need to be tracked and analyzed using this central IT platform. Finally, as we undertake this large-scale workforce transformation, a central IT system will enable Forestland PPS to track open positions and staffing needs across the PPS, essentially creating a job board, so that impacted workers (or those whose current jobs are at risk of elimination) have the ability to see job availability across the member organizations.
Progress Reporting
Please describe how you will measure the success of this organizational workstream and report on progress against your targets.
The headline measures of the success of our workforce transformation program will be the targets of redeployed, retrained, and hired staff and the workforce budget, as articulated in the baseline information to be provided later in DY1. Forestland PPS will utilize an electronic survey mechanism to collect and report this data. We have established a reporting structure for these numbers that allows us to gather information from our whole network on a quarterly basis and funnel this information to the workforce team, who in turn will oversee its reporting. Each of the DSRIP project committees will include a representative of the Forestland PPS Workforce Project Team, in order to ensure the workforce project team has a real-time view of how the recruitment, redeployment and retraining efforts are affecting the individual projects, so that we can manage any risks as they arise. The Workforce Project Team has developed a process to manage the data collection and ratification for the quarterly progress reports, and has communicated this with all organizations in the network.

## Governance
Governance
Key Steps and Measurable Milestones
Domain 1 Process Measures
i. Governance structure updates |  |  | Target Completion Date |  | Supporting Documentation
Milestone: Finalize governance structure and sub-committee structure |  |  | DY1, Q2 |  | Governance and committee structure, signed off by PPS Board. Subsequent quarterly reports will require updates on committee structure and memberships (if relevant).
1. Identify the size and number of standing committees |  |  | DY1, Q1
2. Confirm composition and membership of FHPP Board of Directors |  |  | DY1, Q1
3. Install all members of the FHPP Board of Directors |  |  | DY1, Q1
4. Install all members of the 5 standing committees (Finance, Compliance, IT/Data, Community Initiatives, and Clinical Governance) |  |  | DY1, Q2
Milestone: Establish a clinical governance structure, including clinical quality committees for each DSRIP project |  |  | DY1, Q3 |  | Clinical Quality Committee charter and committee structure chart Subsequent quarterly reports will require minutes of clinical quality committee meetings to be submitted.
1. Draft and adopt Charter for Clinical Committee for FHPP |  |  | DY1, Q2
2. Recruit Membership for Project-level clinical Quality Sub-committees for each of FHPP’s selected projects |  |  | DY1, Q2
3. Draft and adopt Charters for each project-level Clinical Quality sub-committee |  |  | DY1, Q2
4. Identify and adopt evidence-based protocol for each Domain 3 project and others as appropriate |  |  | DY1, Q2
5. Draft and adopt Charters for Emergency Medicine, Behavioral Health, Primary Care and Population Health Management Sub-committees |  |  | DY1, Q2
6. Develop regular meeting schedules for Committee and Sub-Committees |  |  | Dy1, Q3
7. Select/Develop initial metrics for tracking performance |  |  | DY1, Q3
Milestone: Finalize bylaws and policies or Committee Guidelines where applicable |  |  | DY, Q3 |  | Upload of bylaws and policies document or committee guidelines. Subsequent quarterly reports will require PPSs to articulate any updates that have been made to their bylaws, policies or committee guidelines.
1. Develop draft bylaws for review by Board of Directors, Forestland Hospital Center, Forestland Methodist Hospital and Blackbark Medical and Mental Health Center |  |  | DY1, Q2
2. Adopt FHPP Bylaws |  |  | DY1, Q2
3. Identify key policies regarding participation in FHPP governance |  |  | DY1, Q2
4. Draft and adopt dispute resolution policies and procedures |  |  | DY1, Q2
5. Develop, adopt, and communicate policies and procedures regarding non- or under-performing providers |  |  | DY1, Q3
6. Develop and adopt Compliance policies and procedures |  |  | DY1, Q3
ii. Governance process updates |  |  | Target Completion Date |  | Supporting Documentation
Milestone: Establish governance structure reporting and monitoring processes |  |  | DY1, Q4 |  | Governance and committee structure document, including description of two-way reporting processes and governance monitoring processes Subsequent quarterly reports will require minutes of committee meetings, including evidence of two-way reporting between committees.
1. Develop a dashboard to track progress of each DSRIP projects |  |  | DY1, Q2
2. Identify key program metrics to assess workstream progress in financial management, clinical management, workforce management, IT management |  |  | DY1, Q2
3. Develop tools for collecting and reporting data from all participating providers |  |  | DY1, Q3
4. Deploy tools to all participating providers, including Forestland Department of Health and Mental Hygiene (FDHMH), other CBOs and social services agencies |  |  | DY1, Q4
5. Communicate Compliance policies and procedures to the 180 partners and 346 vendors of the FHPP PPS, as appropriate |  |  | DY1, Q3
Key Issues
iii. Community engagement |  |  | Target Completion Date |  | Supporting Documentation
Milestone: Finalize community engagement plan, including communications with the public and non-provider organizations (e.g. schools, churches, homeless services, housing providers, law enforcement) |  |  | DY1, Q2 |  | Community engagement plan, including plans for two-way communication with stakeholders. Subsequent quarterly reports will require evidence of implementation of community engagement plan, including evidence of community engagement events.
1. Identify community resources and organizations participating in activities impacting population health, including food, clothing, shelter assistance |  |  | DY1, Q1
2. Recruit participants for FHPP leadership and participation, in addition to FDHMH |  |  | DY1, Q1
3. Develop schedule of communications and events to stimulate engagement with population health activities |  |  | DY1, Q2
4. Create CBO council to coordinate ongoing outreach and participation, led by FDHMH |  |  | DY1, Q2
Milestone: Finalize partnership agreements or contracts with CBOs |  |  | DY1, Q2 |  | Signed CBO partnership agreements or contracts. Subsequent quarterly reports to require minutes of meetings with CBOs.
1. Negotiate and draft partnership agreements with key CBOs |  |  | DY1, Q2
2. Identify appropriate committees for CBO representation, including Finance |  |  | DY1, Q1
Milestone: Finalize agency coordination plan aimed at engaging appropriate public sector agencies at state and local levels (e.g. local departments of health and mental hygiene, Social Services, Corrections, etc.) |  |  | DY2, Q2 |  | Agency Coordination Plan. Subsequent quarterly reports to require updates on implementation of Agency Coordination Plan, including evidence of interaction with local agencies.
1. Identify all appropriate agencies in the FHPP service area |  |  | DY1, Q1
2. Recruit participants from the various public agencies in coordination with municipal authorities |  |  | DY1, Q3
3. Develop an action plan for coordinating agency activities with the FHPP for discussion, review, and adoption by the Agencies and Municipal Authorities |  |  | DY2, Q1
Milestone: Finalize workforce communication & engagement plan |  |  | DY2, Q1 |  | Workforce communication & engagement plan, including plans for two-way communication with all levels of the workforce, signed off by PPS workforce governance body (e.g. workforce transformation committee). Subsequent quarterly reports to require updates on implementation of workforce communication & engagement plan.
1. Perform Stakeholder Assessment: identify the key stakeholder groups and evaluate their current commitment and the level of commitment required from them for projects to succeed |  |  | DY1, Q2
2. Perform Audience and Vehicle Analyses: Define the communication needs and required key messages by audience group, as well as the available communication channels that can be utilized for stakeholder engagement |  |  | DY1, Q2
3. Develop Workforce Communication and Engagement Strategy: Establish the vision, objectives and guiding principles as a means to engage key stakeholders, signed off by the executive body of the PPS |  |  | DY1, Q3
4. Develop Workforce Communication & Engagement Plan: Outline objectives, principles, target audience, channel, barriers and risks, milestones, and measuring effectiveness, signed off by the executive body of the PPS |  |  | DY1, Q4
iv. Inclusion of CBOs
Explain your plans for contracting with CBOs and their continuing role as your PPS develops over time; detail how many CBOs you will be contracting with and by when; explain how they will be included in project delivery and in the development of your PPS network
The Forestland region has benefitted from the active presence of several CBOs for many decades, and these organizations will be critical to our success through the DSRIP program period, and beyond. The Forestland Soup Kitchens (FSK) has been an active member of our PAC since August, 2014, and will be participating on our Population Health Management Sub-Committee. We have been in discussions with 4 other prominent CBOs about the DSRIP program, and expect to execute provider contracts with at least 5 organizations in total, including FSK, before the end of DY1, Q2. These others leading CBOs have all been asked to participate in our PAC, and include a drug treatment facility (Forestland Recovery), which will participate in our 3.a.i project; the Forestland Visiting Nurse Service, which will participate in several of our projects including 2.a.i; our local chapter of Meals on Wheels; and our local chapter of the Salvation Army. FSK has been active in introducing us the the other 4 organizations mentioned (above), and through those new CBO participants we intend to network further in the CBO community and recruit participation from various social services-focused programs
Major Risks to Implementation & Risk Mitigation Strategies
Please describe the key challenges or risks that you foresee in implementing your governance structure and processes and achieving the milestones described above, as well as potential impacts on specific projects and any risks that will undermine your ability to achieve outcome measure targets.
The key challenges in implementing our governance structure include the ability to recruit and retain the interest and time commitment of key providers and community leaders (above and beyond our capital contributing partners, 2 of which are large hospital centers and 1 of which is a mental health facility). We will need active engagement of community practitioners across the Forestland service area, as well as participation from community-based nursing facilities, home health organizations, and key CBOs, if Forestland PPS is to create an effective collaborative and integrated delivery system. Gaining the cooperation of key providers to invest in developing key capabilities (e.g., EHR, additional staff, etc.) will require a governance process which generates trust through open and active engagement, development of multi-directional communications processes, opportunities for provider and public comment on major developments and initiatives. We will mitigate our risks by creating mutliple communications and collaboration channels, like holding open committee meetings at multiple locations around the Forestland service area, possibly using facilities at the Forestland Public Schools or major houses of worship (e.g., Forestland Epochal Church; Forestland Reform Temple; etc.). Our Forestland Community Portal can open another channel for provider and public comment on issues of concern, which will help inform PPS leadership of where its attention needs to focus. Additionally, we will rely on a fair, balanced and effective funds flow approach to both stimulate and reward community providers to implement project requirements and achieve project goals. This is intended to simultaneously encourage community provider participation in our governance committees and processes. By these means, and the use of segment-elected representatives (e.g., community practitioners electing a member to the Executive Body, along with community nursing facilities electing their representative, Forestland CBOs electing its own representative, etc.), will demonstrate Forestland PPS's commitment to a democratic and open process.
Major Dependencies on Other Workstreams
Please describe the key interdependencies between this and other workstreams (e.g. IT Systems and Processes, Practitioner Engagement, Financial Sustainability etc.)
Effective PPS governance will require several critical factors to be successful, including the availability of accurate data and analytics through an effective IT infrastructure, high levels of communication and commitment among participating providers, an effective and holistic approach to workforce management across highly diverse participating provider organizations, effective and credible funds flow management, and practitioner leadership extending beyond development of EBM (evidence-based medicine) protocols but extending to program and project leadership. Each of these key workstreams need to be operating effectively to facilitate effective PPS governance. Having an IT infrastructure capable of collecting and analyzing key performance metrics is essential to support credible and accurate decision-making. Active and ongoing multi-directional decision-making will be essential to developing and maintaining the trust and engagement of participating providers, and the community at large. The effective commitment of DSRIP funds is required to stimulate participation and reward collaboration while buffering the negative impacts of DSRIP program progress on some provider organizations. Maintaining strong relationships with both unions and other workers will be key to successful delivery system transformation. Practitioner engagement and leadership is critical to not only the development of and compliance with EBM protocols, but with achieving the levels of coordination and collaboration required to eliminate unnecessary duplication of services, getting the right services to the right patients at the right locations, and maintaining the trust and commitment of the practitioner community.
Roles and Responsibilities
Please list the key people/organizations responsible for this organizational workstream and describe what their responsibilities involve. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Role | Name of person / organization (if known at this stage) |  | Key deliverables / responsibilities
| Lead Applicant/Entity | Forestland Health Provider Partnership |  | Bylaw and Policy Development, funding and staff resources
| Major hospital partners | Forestland Hospital Center, Greater Forestland Methodist Hospital |  | Board and Committee members, staff support
| Physician organizations and large practices | Blackbark Medical and Mental Health Center |  | Board and Committee members, EBM protocols
| ACOs, Health Homes | FHC APO, Forestland Health Homes |  | Disease, Case and Care Management Protocols and Procedures
| Major CBOs and/or social service agencies | FDHMH, others as appropriate |  | Board and Committee members, program information, liaisons
| Key advisors, counselors, attorneys, consultants | Forestland Attorneys, LLC., Forestland Financial Services, Tops Consulting Services |  | Drafts governance documents, provider agreements, policies and procedures, etc.
Key Stakeholders
Please identify the key stakeholders involved, both within and outside the PPS with regard to your governance structure and processes. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Key stakeholders | Role in relation to this organizational workstream |  | Key deliverables / responsibilities
Internal stakeholders
| Forestland Hospital Center | Lead Applicant and Equity Contributor, Leadership Participant |  | Funding, leadership personnel, committee chairs, BOD participant
| Greater Forestland Methodist Hospital | Equity Contributor, Leadership Participant |  | Funding, leadership personnel, committee chairs, BOD participant
| Blackbark Medical and Mental Health Center | Equity Contributor, Leadership Participant |  | Funding, leadership personnel, committee chairs, BOD participant
External stakeholders
| Forestland Department of Health and Mental Hygiene | Leadership Participant, |  | Leadership personnel, committee members
| Forestland Farsighted IPA | Participating Provider Organization |  | Leadership personnel, BOD member, Clinical Committee leadership
| Forestland Soup Kitchens | Participating Provider Organization |  | Leadership personnel, PAC member
IT Expectations
Please clearly describe how the development of shared IT infrastructure across the PPS will support this particular workstream and your ability to achieve the milestones described above.
Shared IT infrastructure is essential for the Board of Directors and the various committees to collect and analyze data from all participating providers (180 partners and 346 vendors) to support effective and efficient decision-making for the FHPP. The collection and application of accurate information will form the basis for building and maintaining credibility with the diverse participating providers, as well as with the public in general, and the population to be served in particular. Specifically, maintaining minutes of committee meetings for the multiple governance structures (BOD, Executive, Financial, Clinical and IT committees and their sub-committees) on the Forestland Partner Portal will allow all partners to track progress against milestone goals, while creating a channel for ongoing and inclusive discussion of issues impacting governance of the Forestland PPS. It will also help support needs identification and include ongoing outreach to participating partners to engage them in recruitment efforts for additional community providers (CBOs, clinical resources, others) as the PPS discovers gaps in the network. Additionally, Forestland's IT infrastructure will create channels like the Forestland Provider Portal and the Forestland PPS Public Portal/Forum where stakeholders can communicate issues, concerns, complaints, and even praise (hopefully), to let PPS leadership know what is working well and what requires leadership attention.
Progress Reporting
Please describe how you will measure the success of this workstream.
The success of FHPP governance will be measured against the timely achievement of the creation of the structures (BOD and Committees), the recruitment and empanelment of BOD and committee members, the development and adoption of bylaws, policies and procedures for all key committees and sub-committees, and the development, negotiation and execution of all required provider agreements to allow FHPP to begin operating as a PPS. Additionally, success will be measured by the establishment of the performance management systems (including data collection, analyses and reporting) to support effective and efficient decision-making. For example, the Clinical committee will rely on the performance management systems capturing data regarding achievement of PCMH Level 3 requirements across the PPS network providers, compliance with EBM (evidence-based medicine) protocol, and ultimately with the impact on Program goals (e.g., ED visits).

## Financial Sustainability
Financial Sustainability
Key Steps and Measurable Milestones
Domain 1 Process Measures
i. Financial Sustainability Strategy Updates
Financial Sustainability Strategy Updates |  |  | Target Completion Date |  | Supporting Documentation
Milestone: Finalize PPS finance structure, including reporting structure |  |  | DY1, Q2 |  | PPS finance structure chart / document, signed off by PPS Board. Subsequent quarterly reports will require PPSs to provide minutes of Finance Committee meetings.
1. Establish the financial structure of the Governance organization and the role and responsibilities of the Finance Committee and Compliance Committee and related functions |  |  | DY1, Q2
2. Define the Roles and Responsibilities of the PPS Lead and Finance function |  |  | DY1, Q2
3. Develop charter for the PPS finance function and establish schedule for Finance Committee meetings. |  |  | DY1, Q2
4. Develop PPS Org chart that depicts the complete finance function with reporting structure to Executive Body and oversight committees |  |  | DY1, Q2
5. Obtain PPS Executive Body approval of PPS Finance Function charter and organization structure chart |  |  | DY1, Q2
Milestone: Perform network financial health current state assessment and develop financial sustainability strategy to address key issues. |  |  | DY1, Q3 |  | Network financial health current state assessment (to be performed at least annually). The PPS must: - identify those providers in their network that are financially fragile, including those that have qualified as IAAF providers; -- define their approach for monitoring those financially fragile providers, which must include an analysis of provider performance on the following financial indicators: days cash on hand, debt ratio, operating margin and current ratio; -- include any additional financial indicators that they deem necessary for monitoring the financial sustainability of their network providers In subsequent quarterly reports (i.e. between the annual assessment) PPSs will be requires to provide an update on: --the financial status of those providers identified as financially fragile, including those that qualified as IAAF providers; and how their status impacts their ability to deliver services -- the identification of any additional financially fragile providers; and -- the efforts undertaken to improve the financial status of those providers.
Milestone: Assessment of DSRIP Project Impacts |  |  | DY1, Q2
1. Develop matrix of DSRIP Projects and identify expected impact on provider cost, patient volumes, revenue, LOS or other based upon project goals and participation |  |  | DY1, Q2
2. Review DRAFT of Project Impact matrix with Finance Committee |  |  | DY1, Q2
3. Finalize Project Impact Matrix identifying project participation, expected impact of projects and provider specific view. |  |  | DY1, Q2
4. Review and obtain approval of Project Impact Matrix from Finance Committee and Executive Body as basis for Sustainability and applicable portions of funds flow plan |  |  | DY1, Q2
Milestone: Conduct Current State Financial Assessment and Project Impact Assessment |  |  | DY1, Q3
1. Revise, as needed, Financial Assessment and Project Impact Assessment document(s) that were used for the Preliminary Financial assessment conducted in Nov 2014. Update for required metrics and provider specific metrics. |  |  | DY1, Q2
2. Distribute Current State Financial Assessment and Project Impact Assessment documents to providers |  |  | DY1, Q2
3. Review results of Current State Financial Assessment and Project Impact Assessment returned from providers |  |  | DY1, Q2
4. Prepare report of PPS Current State Financial Status for Executive Body |  |  | DY1, Q3
5 Define procedure for ongoing monitoring of financial stability and obtain approval from Executive Body. |  |  | DY1, Q3
Milestone: Develop Financially Fragile Watch List |  |  | DY1, Q3
1. Based upon Financial Assessment and Project Impact Assessment – identify providers (a) not meeting Financial Stability Plan metrics, (b) that are under current or planned restructuring efforts, or that will be financially challenged due to DSRIP projects or (c) that will otherwise be financially challenged and, with consideration of their role in projects, prepare initial Financially Fragile Watch List and obtain approval of Finance Committee. |  |  | DY1, Q3
Milestone: Develop Financial Stability Plan and obtain approval from PPS Finance Committee |  |  | DY1, Q2
1. Develop PPS Financial Stability plan. The plan will include metrics, ongoing monitoring process, and other requirements. |  |  | DY1, Q2
2. Define process for evaluating metrics and implementing a FSP for the initial Fragile Watch List as well as going forward. |  |  | DY1, Q2
3. Obtain approval of Finance Committee |  |  | DY1, Q2
Milestone: Implement Project Management oversight for Financial Stability Plan and Distressed Provider Plans |  |  | DY1, Q2
1. Define role of PMO for Financial Stability Plan and Distressed Provider Plans and PMO process to manage the plans for the PPS and PPS Lead. |  |  | DY1, Q2
2. Implement PMO oversight for FSP and Distressed Provider Plans – for active plans |  |  | DY1, Q2
Milestone: Define Distressed Provider Plan and obtain approval of Finance Committee |  |  | DY1, Q3
1. Define template for Distressed Provider Plan(s) |  |  | DY1, Q3
2. Define process for evaluating metrics and implementing a DPP for Financially Fragile providers. |  |  | DY1, Q3
Milestone: Finalize Compliance Plan consistent with New York State Social Services Law 363-d |  |  | DY1, Q3 |  | Finalized Compliance Plan (for PPS Lead). Subsequent quarterly reports will require an update on ongoing compliance with 363-d.
1. Complete review of NY Social Services Law 363-d, determine scope and requirements of compliance program and plan based upon the DSRIP related requirements that are within the scope of responsibilities of the PPS Lead. |  |  | DY1, Q3
2. Develop written policies and procedures that define and implement the code of conduct and other required elements of the PPS Lead compliance plan that are within the scope of responsibilities of the PPS Lead. |  |  | DY1, Q3
3. Obtain confirmation from PPS network providers that they have implemented a compliance plan consistent with the NY State Social Services Law 363-d. |  |  | DY1, Q3
4. Develop requirements to be included in the PPS Provider Operating Agreement that the network providers will maintain a current compliance plan to meet NY State requirements for a provider. |  |  | DY1, Q3
5. Obtain Executive Body approval of the Compliance Plan (for the PPS Lead) and Implement |  |  | DY1, Q3
ii. Progress Reports on the PPS Effort to Transition to Value-Based Payment Systems
Progress reports on the PPS effort to transition to value-based payment systems |  |  | Target Completion Date |  | Supporting Documentation
Milestone: Develop detailed baseline assessment of revenue linked to value-based payment, preferred compensation modalities for different provider-types and functions, and MCO strategy. |  |  | DY2, Q3 |  | Value-based payment plan, signed off by PPS board* Subsequent quarterly reports will require updates on implementation of that plan. *Note: PPS Board approval will not prohibit providers’ discretion and ability to contract directly with payers
Milestone: Establish Value Based Payment Work Group |  |  | DY2, Q1
1. Develop VBP Work Group representative of PPS system. Consider representation from PPS providers, PCMH, FQHCs and plans. |  |  | DY2, Q1
2. Develop VBP Work Group Charter. The primary goal of the Forestland VBP Work Group is to coordinate outreach and educational initiatives that support VBP arrangements throughout our system. |  |  | DY2, Q1
Milestone: Develop education and communication strategy for PPS network. |  |  | DY2, Q2
3. Develop education and communication plan for providers to facilitate understanding of value based payment (VBP), to include levels of VBP, risk sharing, and provider/MCO contracting options. |  |  | DY2, Q1
4. Develop educational materials to be used during provider outreach and educational campaign. |  |  | DY2, Q2
Milestone: Conduct Stakeholder Engagement with PPS Providers |  |  | DY2, Q2
5. Conduct education and outreach campaign for PPS system providers to broaden knowledge among the PPS network of the various VBP models and to enable the PPS to employ those models in a coordinated approach (campaign to include in-person and web-based educational sessions for providers). |  |  | DY2, Q2
6. Develop a stakeholder engagement survey to assess the PPS provider population and establish a baseline assessment of (at least) the following This will enable us to make a more informed decision as to the most effective contracting strategy and will inform our contract negotiations with Medicaid plans. Degree of experience operating in VBP models and preferred compensation modalities; Degree of sophistication in ability to negotiate plan contracts, monitor and report on service types; Estimated volume of Medicaid Managed Care spending received by the network. Estimate of total cost of care for specific services (modeled along bundles Status of requisite IT linkages for network funds flow monitoring. Provider ability (financial stability) and willingness to take downside risk in a risk sharing arrangement. Preferred method of negotiating plan options with Medicaid Managed Care organization (e.g. as a single provider, as a group of providers, through the PPS) Level of assistance needed to negotiate plan options with Medicaid Managed Care (High, Moderate, Low). |  |  | DY2, Q1
7. Roll out stakeholder engagement survey to the provider population to determine PPS baseline demographics. |  |  | DY2, Q1
8. Conduct provider outreach sessions to supplement the stakeholder engagement survey and engage stakeholders in open discussion. |  |  | DY2, Q2
9. Compile stakeholder engagement survey results and findings from provider engagement sessions and analyze findings. |  |  | DY2, Q2
Milestone: Conduct stakeholder engagement with MCOs |  |  | DY2, Q2
10. Conduct stakeholder engagement sessions with MCOs to understand potential contracting options and the requirements (workforce, infrastructure, knowledge, legal support, etc.) necessary to conduct and finalize plan negotiations. |  |  | DY2, Q2
11. Forestland PPS Board to sign off on preference for PPS central role in contracting. |  |  | DY2, Q1
Milestone: Finalize PPS VBP Baseline Assessment |  |  | DY2, Q2
12. Develop initial PPS VBP Baseline Assessment, based on feedback from provider and MCO stakeholder engagement sessions and survey results, providing an overview of the Forestland PPS provider population (by provider type and specialty areas, a view of preferred compensation modalities, and a detailed overview of contracting options. |  |  | DY2, Q2
13. Circulate the Forestland PPS VBP Baseline Assessment for open comment among network providers to help ensure accuracy and understanding. |  |  | DY2, Q2
14. Update, revise and finalize Forestland PPS VBP Baseline Assessment. |  |  | DY2, Q2
Milestone: Finalize a plan towards achieving 90% value-based payments across network by year 5 of the waiver at the latest |  |  | DY2, Q3 |  | Value-based payment plan, signed off by PPS board* Subsequent quarterly reports will require updates on implementation of that plan. *Note: PPS Board approval will not prohibit providers’ discretion and ability to contract directly with payers
Milestone: Prioritize potential opportunities and providers for VBP arrangements. |  |  | DY2, Q2
1. Analyze health care bundle populations and total cost of care data provided by the Greater Forestland Department of Health (DOH), to identify VBP opportunities that are more easily attainable and prioritize services moving into VBP. |  |  | DY2, Q1
2. Identify VBP accelerators and challenges within Forestland PPS related to the implementation of the VBP model, including existing ACO and MCO models with current VBP arrangements, existing bundled payments, or shared savings arrangements a, and necessary IT infrastructure that can be utilized to monitor VBP activity (accelerators); and contracting complexity, limited infrastructure with experience in VBP or abundance of low performing providers (challenges). |  |  | DY2, Q2
3. Align providers and PCMHs to potential VBP accelerators and challenges to identify which providers and PCMHs are best aligned to expeditiously engage in VBP arrangements. |  |  | DY2, Q2
4. Identify providers and PCMHs within the PPS with the greatest ability to negotiate VBP arrangements and operate in a VBPO model. Providers and PCMHs will be divided into three categories (Advanced, Moderate and Low) based on 1) findings derived from the VBP Baseline Assessment, 2) their alignment with VBP accelerators and challenges, and 3) their ability to implement VBP arrangements for more easily attainable bundles of care based on DOH provided data. |  |  | DY2, Q2
5. Conduct engagement sessions between ‘advanced’ providers/PCMHs and MCOs to discuss the process and requirements necessary for engaging in VBP arrangements. |  |  | DY2, Q3
6. Re-assess capability and infrastructure of providers and PCMHs that have been identified as ’advanced,’ in order to assess for strengths and weaknesses in ability to continue as early adopters of VBP arrangements. |  |  | DY2, Q2
Milestone: Develop timeline for VBP adoption. |  |  | DY2, Q3
7. Develop a realistic and achievable timeline for “Advanced” providers and PCMHs to become early adopters of VBP arrangements, taking into account findings of the baseline assessment, alignment with VBP accelerators, and ability to engage in VBP arrangements for the care bundles deemed more attainable and which are supported by DOH data. |  |  | DY2, Q2
8. Allow for the recording of lessons learned from “Advanced” providers’ engagement with VBP arrangements. |  |  | DY2, Q3
9. Develop phases 2 and 3 for “Moderate” and “Low” providers and PCMHs to adopt VBP arrangements using lessons learned, and develop early planning states for advanced providers to move into Level 2 arrangements when appropriate. |  |  | DY2, Q3
10. Engage key financial stakeholders from MCOs, PPS and providers to discuss options for shared savings and funds flow. Key elements of this step will include effectively analyzing provider and PPS performance, methods of dispersing shared savings and infrastructure required to support performance monitoring and reporting. |  |  | DY2, Q3
Milestone: Finalize VBP Adoption Plan |  |  | DY2, Q3
11. Collectively review the VBP Adoption Plan with the PPS. |  |  | DY2, Q3
12. Update, modify and finalize VBP Adoption plan. |  |  | DY2, Q3
NOTE: PPSs will ultimately be required to set target dates for the following three milestones, as well as the milestones above. However, this will not be required until the VBP Roadmap is confirmed and all milestone targets are finalized. A detailed timeline setting out the due dates for all the elements of the implementation plan that are not required by April 1st will be published shortly.
Milestone: Put in place Level 1 VBP arrangement for PCMH/APC care and one other care bundle or subpopulation
Step 1…
Step 2…
Milestone: Contract 50% of care-costs through Level 1 VBPs, and ≥ 30% of these costs through Level 2 VBPs or higher
Step 1…
Step 2…
Milestone: ≥90% of total MCO-PPS payments (in terms of total dollars) captured in at least Level 1 VBPs, and ≥ 70% of total costs captured in VBPs has to be in Level 2 VBPs or higher
Step 1…
Step 2…
Major Risks to Implementation & Risk Mitigation Strategies
Please describe the key challenges or risks that you foresee in implementing these cross-cutting organizational strategies, including potential impacts on specific projects and, crucially, any risks that will undermine your ability to achieve outcome measure targets.
There are challenges to implementing the organizational strategies required for the financial sustainability workstream that could impact Forestland Health PPSs efforts to assess and monitor the financial health of the PPS providers and to establish the role of the Forestland Medical Center (FMC) as the PPS Lead responsible for the administrative and operational aspects of the PPSs finance function. These challenges include the following: • Implementation of a financial reporting infrastructure • Obtaining buy-in of the Forestland PPSs DSRIP project and funds plans • Inability to access data to perform or validate analytics related to project performance • Failure of PPS providers to meet the DSRIP reporting requirements The high-level IT current state assessment that was conducted for our DSRIP application revealed a lack of financial reporting infrastructure amongst many of our providers. The implementation of a shared reporting infrastructure is essential to having timely access to the financial metrics needed to monitor the financial health of the PPS providers. This is therefore a key risk for our Finance Function and they will be involved in the IT Function’s implementation and management of a shared IT infrastructure throughout the network. In addition, links to sources of performance data will enable the Forestland PPS finance function to have timely access to both financial and performance data to identify trends that might negatively impact the PPS and to implement plans of corrective action and to update reporting that impacts the DSRIP payments. In addition to our ability to access financial metrics for our providers related to their financial health, the timely reporting of data and metrics related to project status and performance is essential to meeting the PPS’s DSRIP reporting requirements. We have developed a Data and Technology workplan specifically related to the requirements that the finance function has for DSRIP project related metrics and data. In addition, the Forestland PPS DSRIP Finance Calendar will be distributed to all PPS providers regularly to update them on the schedule for submitting reporting information to the PPS as needed for submission to DOH. The Forestland PPS recognizes the importance of having buy-in of the PPS providers to the functioning of the integrated delivery network and to the goals and objectives of DSRIP – even in those instances where those objectives might negatively impact their business model. Having the buy-in and support of the providers is essential to meeting the DSRIP project requirements and to earning the full DSRIP payment. To obtain, and sustain, this important buy-in we will develop strong lines of informative and meaningful communication to the providers. We will establish a funds distribution plan that is transparent to the providers and ensure that all plan requirements and related processes and payment schedules are clearly understood and communicated regularly. Transitioning away from a fee-for-service reimbursement methodology toward a VBP model represents a considerable change in business practice for many of the providers within the Forestland PPS network, and a significant challenge particularly to some of our smaller providers and those who are less advanced in terms of operating in a VBP model. These providers will require assistance in a number of areas to facilitate their transition toward contracting in VBP arrangements. Some of our providers lack the knowledge and experience of non-fee for service models that would otherwise enable a more expeditious transition toward VBP arrangements on their own behalf. We will facilitate the transition toward VBP arrangements for our PPS provider population through educational and marketing campaigns. These campaigns will cover the objectives of value-based payment models, as well as the possible implications of engaging in VBP arrangements, such as risk sharing, empowering our providers to make more sound and intelligent decisions toward their potential and pace at which they can achieve VBP arrangements. As we identified in our initial DSRIP PPS Organizational Application, Forestland will engage partners to develop a flexible, multi-phased approach that enables the most appropriate and effective method of contracting on a VBP basis within our region. However, we also recognize this task as a challenging process where many considerations, such as contracting complexity and existing provider/MCO relationships must be taken into account. To address this challenge, our approach will take into account the strong relationships that exist between individual providers and MCOs and we will enable our providers to contract directly with MCOs in our region. To successfully operate in a VBP arrangement, our partners must maintain a firm understanding of the varying degrees of risk sharing, capitation and fee for service. Forestland PPS will examine opportunities to facilitate and support contract negotiations between our PPS providers and MCOs, to the greatest extent possible. We intend on examining opportunities for standardization in contracting methodologies among MCOs, ultimately streamlining our partners in their ability to establish VBP arrangements. And finally, as with all entities responsible for compliance in healthcare and finance related fields, the Forestland PPS recognizes that there is a risk that compliance requirements will not be followed or that loss of funds may occur within the finance function. We are developing a robust compliance plan applicable to the PPS Lead functions performed by FMC that will establish policies, procedures, and guidelines for operating within the compliance requirements of NY State. In addition we will implement an active education and training initiative to ensure that everyone is aware of the compliance rules and procedures as well as to instruct them on procedures to follow to report or discuss compliance related actions or concerns.
Major Dependencies on Other Workstreams
Please describe any interdependencies with other workstreams (IT Systems and Processes, Clinical Integration, etc.)
During our preliminary assessment of the finance function for the Forestland PPSs DSRIP application we identified a number of interdependencies with other workstreams in key areas which we have outlined below. • Governance – A fully supportive governance process is essential to establishing the role of the Forestland Medical Center as PPS Lead. In addition, fully established roles within the governance structure for Finance, Compliance and Audit will inform and drive the finance committee charter, its oversight of the finance function and approach to funds flow. • DSRIP Network Capabilities and Project Implementation - The successful implementation of Forestland Health’s value based reform strategy, and execution of value based contracts, will require a developed and functioning integrated delivery network and buy-in of the network partners to the value based payment strategy. • Reporting Requirements – The DSRIP process has extensive reporting requirements linked to DSRIP payments – such as the quarterly reporting is a dependency for receiving DSRIP Process Payments. This reporting is dependent upon input and submission of reports and data from the individual network providers as well as other sources of data that will require the PPSs IT function to access.  DSRIP Projects – The Forestland PPS finance function must have an understanding of projects selected and participation level of providers for each (Provider Participation Matrix) in order to develop a meaningful funds plan for the PPS. In addition, the PPS and the providers must understand project costs, impacts and other needs as part of their process of evaluating financial stability and impact going forward. • IT and Data – This workstream will be essential to providing technology to access data and to implement shared financial reporting infrastructure that is needed by FMC as well as the technology for reporting project level performance data that is closely linked to the payments received for DSRIP projects. • Workforce – The impact of the DSRIP projects is still being reviewed as is the costs related to those impacts and the strategies of the PPS and each provider to mitigate that impact. FMC will work closely with the workforce workstream to ensure that the appropriate data related to the workforce strategy and impact is being gather and reported to meet the DSRIP requirements. FMC is responsible for communicating these requirements for tracking and reporting to all PPS providers to ensure that the PPS meets its requirement to report this information to DOH.
Roles and Responsibilities
Please list the key people/organizations responsible for this organizational workstream and describe what their responsibilities involve. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Role | Name of person / organization (if known at this stage) |  | Key deliverables / responsibilities
| Director of Finance/Accounting | Jame Parkerson |  | Responsible for development and management of the Finance Office and its specific functions. The individual will provide guidance and oversight around the Funds Flow Plan, the Financial Stability Plan, and other relevant processes. The responsibilities include ensuring that funds are managed and distributed according to the approved plan, that reporting requirements are met and that communication regarding the Finance related functions is timely and accurate.
| Accounting Manager | Iliana Fetterof |  | Responsible for the daily operation of the Finance Office, including programmatic development of the infrastructure tools critical to the Funds Flow Plan and the related banking, accounts payable and general ledger functions.
| Financial Analyst | Geralyn Granillo |  | Responsible for assisting in the continuity of operations of the data aspects of the Finance Office and providing assistance to the Finance Office as it relates to data analysis, acquisition and reporting. This position will be responsible for developing and distributing the defined report data set(s) to the designated stakeholders.
| Accounts Payable Staff | Francine Santiago Katharine Silvester |  | Responsible for the day-to-day operations of the Accounts Payable function, including updating policies and procedures, monitoring the accounts payable system, and developing protocols around reporting and AP check write related to the DSRIP funds distribution.
| Reporting Analyst(s) | Mana Florian |  | This position(s) will be responsible for working with the Director of Finance to determine and monitor the reporting protocols/requirements for the PPS providers, the governing body, and DOH.
| Banking Staff | Gene Suhr Kaleigh Oja |  | Responsible for the day-to-day operations of the Banking function, including the processing of the DSRIP funds received from DOH and reporting of the status of funds expected and received as well as reconciliation of bank related statements.
| Compliance Director | [TBD] |  | Will oversee the development and implementation of the compliance plan of the PPS Lead and related compliance requirements of the PPS as they are defined. Scope would include the PPS Lead compliance plan related to DSRIP. The compliance role should report to the Executive Body.
| Audit | [TBD] |  | External auditors reporting to the Finance Committee. The firm will perform the audit of the PPS and PPS Lead related to DSRIP services according to the audit plan approved by the Finance Committee and Executive Body
| VBP Project Manager | [TBD] |  | Coordinate overall development of VBP baseline assessment and plan for achieving value based payments.
| VBP Baseline Functional Lead | [TBD] |  | Coordinate approach and engagement of process to develop PPS VBP Baseline Assessment and Adoption Plan. Ultimately responsible for the development of the PPS VBP Baseline Assessment and Adoption Plan. Will report to the VBP Project Manager.
Key Stakeholders
Please identify the key stakeholders involved, both within and outside the PPS. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals and organizations responsible for driving/managing the workstream, whereas the 'Key Stakeholders' table is intended to capture the people/organizations with a stake in the project, but who are not directly responsible for driving it.
| Key stakeholders | Role in relation to this organizational workstream |  | Key deliverables / responsibilities
Internal stakeholders
| April Greenthumb | PPS DSRIP Project Director |  | The DSRIP Project Director has overarching responsibility for oversight of the DSRIP initiative for the PPS
| Bob Hollow | Project Management Office |  | PMO oversight and leadership for finance related projects, VBR strategy, and for the overall implementation plan deliverables that affect finance function reporting
| Catherine Ivanov | DSRIP Project Leads |  | Collaboration with finance re: PPS Project Implementation, status of project, reporting required to meet DOH requirements,
| Daniel Jackson PPS Compliance Officer | PPS Compliance Committee PPS Compliance Officer |  | Oversight of PPS Compliance Plan and related training, education, and reporting requirements of the plan
| Eric Koen Manager Internal Audit | Internal Audit |  | Oversight of internal control functions; completion of audit processes related to funds flow, network provider reporting, and other finance related control processes
| Forrest Lander Finance Committee Chair | PPS Finance Committee |  | Board level oversight and responsibility for the PPS Finance function; Review and approval of finance related policies and procedures; oversight of PPS Lead role, responsibilities and deliverables; oversight of audit and compliance related processes
| George Masterson Human Resources | PPS Human Resources |  | HR related functions of PPS for its employees and guidance related to the PPS workforce strategies
| Hank Neville IT Department | PPS IT Department |  | Information Technology related requirements for the finance function; access to data for the finance function reporting requirements
| CEOs of PPS Network Partners | - |  | PPS Network Provider partners’ CEOs are responsible for their organization’s’ execution of their DSRIP responsibilities, they will contribute to the success of the finance function and finance related strategies
| CFO/Finance Team of PPS Network Partner | - |  | Primary contact for the PPS Lead finance function for conducting DSRIP related business and responsible for their organization’s execution of their DSRIP related finance responsibilities and participation in finance related strategies
| Boards of Directors for PPS Network Partners | - |  | PPS Network Provider partners’ BOD have overall responsibility for their organizations’ execution of their DSRIP responsibilities, they will contribute to the success of the finance function and finance related strategies
External stakeholders
| Kerry Quintin External Audit Function | External Audit Function |  | External Audit Function
| MCOs and other payers | MCOs and other payers identified by PPS for pursuit of PPS Value based reform strategies |  | The PPS Lead and PPS will have responsibilities related to implementing the PPSs value based strategy, the contracting process, and implementation / administration of executed value based agreements.
| NY DOH | NY DOH defines the DSRIP requirements |  | The PPS Lead and PPS finance function has responsibility for the overall administration of DSRIP reporting to DOH and the funds flow process
| Community Representatives | Community Representatives |  | Community needs and interests are significant influencers of DSRIP projects and will contribute to the adoption and buy-in across the network. Communication regarding DSRIP status, results, and future strategies will be important to maintain their contribution and influence.
| Government Agencies / Regulators | Government Agencies / Regulators\ |  | County and State agencies and regulatory bodies will have oversight and influence in a number of DSRIP related areas - including the importance of waivers or regulatory relief, construction / renovation projects, and other items related to DSRIP. Communication with them regarding DSRIP status, results, future strategies and their role in DSRIP success will be important.
| Medicaid Managed care Plans | Responsible for contracting with Forestland and individual providers on a VBP basis. |  | These will be determined pursuant to the development of Forestland’s Baseline Assessment and VBP Adoption Plan.
| HIV Special Needs Plans | Responsible for contracting with Forestland and individual providers on a VBP basis for the HIV population specialty chronic population. |  | These will be determined pursuant to the development of Forestland’s Baseline Assessment and VBP Adoption Plan.
IT Expectations
Please clearly describe how the development of shared IT infrastructure across the PPS will support this particular workstream.
The development of shared IT infrastructure across Forestland PPS will support the Forestland PPS Finance Office and our work on the financial sustainability of the network by providing the network partners with capability for sharing and submitting reports and data pertaining to project performance and other DSRIP related business in a secure and compliant manner. We have begun the process of establishing a shared financial reporting platform across the network, which will be utilized to provide access and visibility to updates on key financial sustainability metrics at the provider and PPS level. We also intend to link to the performance reporting mechanisms that will be utilized across the PPS to provide our finance team with current data that may be utilized to track project performance levels and expected DSRIP payments. Other shared IT infrastructure and functionality across the PPS that will support or contribute to the success of the Forestland PPS Finance Office includes: • Population Health systems or technology that will support the need to access and report on data related to clinical services and outcomes – for DSRIP required metrics and to meet the needs under value based payment arrangements. • Care Coordination technology and systems that supports broad network integration of services and health management capabilities.
Progress Reporting
Please describe how you will measure the success of this organizational workstream.
We will align our PPS financial management and sustainability progress reporting with the reporting and oversight structures in place for the DSRIP projects, through the Forestland PPS PMO. The PMO will be responsible for monitoring progress against project requirements and process measures at a provider level, and the preparation of status reports for the quarterly reporting process for DOH. We have integrated into this process the financial reporting that we require in order to be able to monitor and manage the financial health of the network over the course of the DSRIP program. The Forestland PPS Finance Office will be responsible for consolidating all of the specific financial elements of this project reporting into specific financial dashboards for the Forestland PPS Board and for the tracking of the specific financial indicators we are required to report on as part of the financial sustainability assessments and the ongoing monitoring of the financial impacts of DSRIP on the providers. Through ongoing reporting, if a partner trends negatively or if the financial impacts are not in line with expectations, the Forestland PPS Finance Office will work with the provider in question to understand the financial impact and develop plans for corrective action. The Forestland Finance Office will provide regular reporting to the Finance Committee, Executive Body and network partners as applicable regarding the financial health of the FHPP and updates regarding the Financially Fragile Watch List and the Distressed Provider Plans currently in place.

## General Project Implementation
General project implementation section
This General Project Implementation section will apply across all of your DSRIP projects. In this section you describe your PPS's overall approach to the implementation of your DSRIP projects, as well as some of the factors that will apply to all projects – such as your PPS’s approach to prject performance monitoring. You will be required to provide an update on these headings in each quarterly report, although there will be no specific achievement value attached to these updates.
Overall approach to implementation
Please summarize your intended approach to the implementation of your chosen DSRIP projects, including considerations around how this approach will allow for the successful development of concurrently implementing DSRIP projects
The overall approach that Forestland PPS is taking towards the implementation of its eleven DSRIP projects is based on delegated leadership, meaningful education and communication throughout the process, and a strong push for standardization of clinical and operational protocols. The first piece of this approach is strong delegated leadership. Forestland’s large provider network requires alignment of divergent interests in order to meet the milestones and goals of the projects we are undertaking, as well as the overarching goals of the DSRIP program. With the delegated governance model taken on by Forestland PPS, each project will have its own leadership team, including both clinical and operational leaders, representing a broad range of the providers in our network, in charge of day-to-day project management and responsible for the detailed tracking of milestones and metrics at a provider level. These project leadership groups will all report in to the Forestland PPS Project Management Office (PMO), which will be responsible for driving the overall timeline and deliverables of the projects. Deliverables or targets that span across the PPS (such as the Forestland PPS bed reduction strategy and the quarterly reporting on speed of implementation measures) will be managed centrally by separate groups within the PMO. This approach to project management and leadership will give the PPS both the flexibility to adapt projects to respond to changing circumstances, and the oversight to ensure clinical coordination between projects. The second piece of Forestland’s approach to implementing and managing the DSRIP projects is a strong focus on education and open and transparent communication that flows both ways. We understand that it is important that information generated centrally is quickly disseminated among all partners in the network. Likewise, it is important for the information to make its way quickly from the network back up to the central offices. We intend to make use of the Medicaid Innovation eXchange (MIX) to create a space for our own PPS members, where we can post materials centrally, host online discussions and gather feedback and input. The MIX will also serve as a platform on which we will post our current progress towards the DSRIP goals so that all that are interested may see how we are faring against our collectively determined targets. We are also investigating the possibility of using the MIX as the vehicle to gather the materials needed for the quarterly reporting process. As practice models shift and Forestland PPS’s provider network becomes increasingly integrated, it will be necessary for providers and clinicians to be educated on: (a) what these DSRIP-driven changes mean for their practice and how they will be affected at each step of implementation; and (b) what their role, expectations, and obligations are. Education and provider inclusion will be one of the key roles of our Clinical Quality Committee and its sub-committees for each project. Provider education is also a two-way process and we intend to work with the State to be involved in both the project breakthrough series and the annual learning collaborative conferences to maximize the impact of our DSRIP projects. As mentioned above, we intend to utilize a space on the Medicaid Innovation eXchange (MIX) platform to increase connectivity between PPS members and have a central space for disseminating and posting PPS materials. The process of standardizing clinical and operational protocols is likely to be the most difficult task facing the Forestland PPS PMO. It is not just about aligning systems, but also achieving a common language between providers, a common method of performance measurement for the PPS, and a common culture focused on patient outcomes – all of which will underpin the transition to VBP. The following initiatives are central to our drive for increasing standardization across our network: - The development of shared IT infrastructure and data sharing – ensuring that patient information is seamlessly and securely transferred. This work will be led by the Forestland IT Transformation Group but each of the project leadership teams will have regular representation in the meetings and committees of this work group. - Our care transitions strategy (led by our Clinical Quality Committee) and the buy-in to this strategy from practitioners throughout the network. One element in achieving this buy-in will come from the role played by the cross-PPS professional networks that will be involved in the design of the care transitions strategy. - The sharing of best practice and performance information, through the network of project clinical committees, the project-focused breakthrough series and the annual learning collaboratives - The hiring, training, and redeployment of staff that will happen as part of our workforce transition strategy – in particular, we will ensure that the (re)training of staff creates a workforce with a consistent, multi-disciplinary approach to care delivery
Major dependencies between work streams and coordination of projects
Please describe how your approach will handle interdependencies between complementary projects, as well as between projects and cross-cutting PPS initiatives - for example, an IT infrastructure upgrade, or the establishment of data sharing protocols.
Since Forestland PPS is one of the larger PPSs in the DSRIP program, and since it is undertaking the maximum amount of projects, interdependencies between projects and between cross-cutting PPS-development initiatives are inevitable, and will make the implementation of our DSRIP projects highly complex. In particular, our concern is that different projects will be working towards similar goals or project requirements independently, thereby doubling effort and potentially creating multiple approaches to solving the same issue. For example, managing transitions of care more effectively will be a central part of multiple projects and without a proactive approach to our Care Transitions Strategy there is a risk that different protocols will be developed at different sites or in different projects. Many projects also share same or similar project requirements. Taking that into account, we have taken a robust approach to predicting, planning for, and managing the overlap between project requirements. Our main overlap with other PPSs occurs to the North and the South where we share approximately 10% of our provider network with the Concreteville and Riverside PPSs. Given this overlap and our joint responsibility to achieve Domain 4 population health goals we have collectively decided to create an overarching Area Committee consisting of the PMO leads for the Forestland, Concreteville and Riverside PPSs. This committee is to be responsible for identifying issues of overlap, monitoring collective progress towards Domain 4 goals and setting up plans to prevent unnecessary waste of funds in the fringe areas between the PPSs. To deal with the overlapping project requirements we have mapped out all of the project requirements affecting all of our committed providers and developed a ‘heat map’ of the project requirements that show where they cross-cut and which providers will be involved in the most projects. For those project requirements that are most pervasive, we have set up specific teams tasked with driving consistent, coordinated implementation. For example, achieving PCMH 2014 Level 3 certification will be a priority for many providers and will be an important success factor in many projects. We have therefore set up a dedicated PCMH Certification Team that will be responsible for all relevant providers meeting this project requirement according to the timetable set out in our project speed of implementation forecasts. In our heat map we have also identified and set up task teams for the following most overlapping requirements: - Use of EHRs to track all patients engaged in projects; - Ensure that all PPS safety net providers are actively sharing EHR systems with local HIE/RHIO/SHIN-NY and sharing health information among clinical partners by the end of Demonstration Year (DY) 3; - Ensure that EHR systems used by participating safety net providers meet Meaningful Use and PCMH Level 3 standards by the end of DY 3; and - Establish agreements with the Medicaid MCOs serving the affected population to provide coverage for the service array under a specific project. We have also used this provider / requirement heat map as the starting point for identifying the clinical, financial, administrative, or technological initiatives that will be most important for the successful delivery of our DSRIP projects. These initiatives will receive specific attention from the Forestland PPS PMO. This heat map will also drive a timeline of the most prevalent project requirements, which will be managed and led by the Forestland PPS PMO, as opposed to the other, more project-specific requirements, which will be driven by the individual project leadership teams.
Overview of key stakeholders and how influenced by your DSRIP projects
In the below table, please set out who the key stakeholders are that play a major role across multiple DSRIP projects. Please give an indication of the role they play and how they impact your approach to delivering your DSRIP projects. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals driving/managing the projects, whereas the 'Key Stakeholders' table is for the people/organizations with a stake in the projects, but who are not responsible for driving them.
| Key stakeholders | Role in relation to your DSRIP projects | Key deliverables / responsibilities
Internal stakeholders
| Forestland PPS Finance Function (FPFF) | Financial impact monitoring | FPFF will be responsible for ongoing monitoring of the impact of the DSRIP projects on the financial health of the network and individual providers A member of the FPFF will be embedded within the PMO
| Forestland Workforce Project Team (FWPT) | Managing the delivery of the workforce transformation strategy through the DSRIP projects | The FWPT will consolidate and manage the (re)training, redeployment and new hire needs of each of the projects. The FWPT will be responsible for the quarterly reporting of workforce transformation numbers Individual project leadership teams will report all of their workforce needs up to the FWPT
| Forestland IT Transformation Group (FITG) | Managing the IT needs of individual projects | The FITG will be responsible for managing the various PPS-wide IT & data transformation initiatives The FITG will have a representative in the Forestland PMO in order to ensure these initiatives impact successfully on each of the DSRIP projects
| Professional groups | Ensuring professional groups are engaged in projects | Alongside the clinical quality committees, the professional groups (e.g. Pediatrician community of practice, Community health worker community of practice etc.)
| Compliance Committee | Ensures PPS compliance on all relevant fronts | Review PPS’s conduct in terms of adherence to DSRIP guidelines, laws, and regulations
| Community Initiatives Committee | Manages PPS relations with patients and CBOs | Coordinate patient and community outreach and communication
| Integrated Delivery System Workgroup (IDSW) | Manages the clinical integration process | The IDSW is the leadership team for Project 2.a.i As well as the delivery of the project requirements for project 2.a.i, the IDSW is responsible for securing the active involvement of all providers in the PPS network into the integrated delivery system
| Cultural Competence Committee | Manages the cultural competency and health literacy transformation process | Develop, distribute, and operate the cultural competency educational program Develop, distribute, and operate the health literacy patient program
External stakeholders
| Patient Voices | Patient / User group | We have engaged with Patient Voices, a local patient representative group, to ensure that their views and insights help to drive the implementation of our DSRIP projects The Forestland PMO will be responsible for regular engagement with Patient Voices and for guiding their role in relation to the individual DSRIP projects
| ABC Labor Union | Labor representation | We have engaged with ABC Labor Union to discuss our plans for workforce transformation; as these plans are delivered through the implementation of the DSRIP projects, we will continue to engage with them on the specific changes to the workforce
| The Forestland Alliance on Mental Illness (FAMI) | Project implementation support | Forestland PPS has engaged with the Alliance to support our implementation planning for Project 3.a.i. We will continue to draw on their support throughout the implementation of this project and to inform our overarching plans for clinical integration
| Forestland Office of Mental Health (FOMH) | Project implementation support | Provide insight into best practices with respect to the implementation of all projects – Project 3.a.i in particular – and support to our Forestland Clinical Quality Committee
| Forestland Office for People with Developmental Disabilities (FOPWDD) | Project implementation support | Provide insight into best practices with respect to the implementation of all projects – Project 3.a.i in particular – and support to our Forestland Clinical Quality Committee
| Forestland office of Alcoholism and Substance Abuse Services (FOASAS) | Project implementation support | Provide insight into best practices with respect to the implementation of all projects – Project 3.a.i in particular – and support to our Forestland Clinical Quality Committee
| Forestland Office for the Aging (FOFA) | Project implementation support | Provide insight into best practices with respect to the implementation of all projects with respect to aging populations, and support to our Forestland Clinical Quality Committee
| Forestland Medical University | Engage in providing education | Provide insight into best practices with respect to the projects implementation and healthcare delivery, workforce training/education, and potentially adjusting core curriculum to reflect healthcare transformation enforced through the DSRIP program.
| Concreteland PPS | Collaborate in Domain 4 project implementation | Collaborate in the implementation of the Domain 4 projects accounting for the overlap in counties and network providers, including the prevention of redundancy and waste of resources.
| Riverside PPS | Collaborate in Domain 4 project implementation | Collaborate in the implementation of the Domain 4 projects accounting for the overlap in counties and network providers, including the prevention of redundancy and waste of resources.
Roles and responsibilities
Please outline the key people & organizations that play a role in the delivery of your PPS’s DSRIP projects, as well as what their responsibilities are regarding governance, implementation, monitoring and reporting on your DSRIP projects. To clarify, the 'Roles & Responsibilities' table is intended to capture those individuals driving/managing the projects, whereas the 'Key Stakeholders' table is for the people/organizations with a stake in the projects, but who are not responsible for driving them.
| Role | Name of person / organization (if known at this stage) | Key deliverables / responsibilities
| Forestland PPS PMO | Overarching program management | PMO will be responsible for delivering quarterly reports to DOH Project leadership teams will report into PMO PMO will manage any major risks that are escalated from Project leadership teams PMO will be responsible for driving the implementation of those projects requirements identified as the most pervasive (through the heat map described above) PMO will monitor the implementation of cross-PPS organizational development initiatives, such as IT infrastructure development and workforce transformation PMO will be the link between the Project leadership teams and the Forestland Finance Office, the Forestland workforce Project Tea, the Forestland IT transformation Group, and the Forestland PPS Compliance Committee
| Forestland PPS Clinical Quality Committee (FCQC) | Oversight of the clinical quality committees for individual projects | FCQC will ensure project-specific clinical quality committees are effectively driving improvements in clinical outcomes and improved clinical integration; Project-specific clinical quality committees will escalate any major quality issues / risks to the FCQC; FCQC will ensure any overlap between project-specific clinical quality committees is managed (for example, where there is considerable overlap between two of our projects, we may consider merging the two clinical quality committees) FCQC will oversee and sign off the performance metrics for each of the DSRIP projects FCQC will be education network providers on the details of project implementations
| Project-specific leadership teams | Project management | Day-to-Day management of progress against Project requirements Reporting on progress against Project requirements to Forestland PPS PMO Managing clinical integration at A Project level and Compliance with PPS initiatives such as Care Transitions Strategy implementation of Project-specific workforce initiatives – i.e. the retraining, hiring, redeployment required by each specific Project
IT requirements
Information technology will play a crucial role in the development of an effective, integrated performing provider system. It is likely that most projects will require some level of supporting IT infrastructure. Please describe the key elements of IT infrastructure development that will play a role in multiple projects.
There are several key pieces of IT infrastructure, beyond project-specific or provider-specific elements, that will play a significant role in multiple – and in some cases all eleven – DSRIP projects being undertaken by Forestland PPS. The timing of the development of these IT systems and data sharing protocols will be based on the relative necessity for the implementation of the DSRIP projects, with the project requirement ‘heat map’ being the starting point for identifying the elements of IT infrastructure development that are most critical to the delivery of the DSRIP projects. The IT current state assessment carried out prior to our DSRIP application identified a lot of variation between providers in the network in terms of the sophistication of their use of electronic patient information. The program of work being driven by the Forestland PPS IT Transformation Group will drive greater use of interoperable health IT platforms. The PMO will be responsible for ensuring that each of the DSRIP projects is tied into the delivery of this program of work. Two of the key multi-project IT systems that the Forestland PPS IT Transformation Group will be driving are: (1) the new EHR recently implemented at the PPS Lead, Forestland Hospital Center; and (2) the Population Health System built out for its Health Home. These two systems have already been tried and tested by Forestland Hospital Center and proven to have the potential to drive integration and effective communication across the PPS. The EHR system and the Population Health System will serve as the starting point for IT standardization efforts. These two systems, due to their widespread functionality, will play a major role in a majority of Forestland PPS’s chosen projects. However, the delegated approach to project implementation described above will allow us to tailor these efforts to the requirements of particular projects and the providers involved in them. The primary objectives driving IT implementation are (1) achieving active participation and effective usage of the EHR system and patient registries for all providers in the system by the end of Demonstration Year 2; (2) meeting Meaningful Use and PCMH Level 3 standards for all relevant providers by the end of Demonstration Year 3; and (3) connecting to the local HIE to ensure the availability of clinical data as well as the ability to share it amongst the appropriate PPS providers.
Performance monitoring
Please explain how your DSRIP projects will fit into your development of a quality performance reporting system and culture.
The DSRIP projects are central to the execution of the four pillars of effective rapid-cycle evaluation, as outlined in our DSRIP application: (1) a culture devoted to optimizing outcomes for patients; (2) clear responsibilities and accountability of staff for these outcomes; (3) optimizing and standardizing processes that we deem vital to realize these outcomes; and (4) continuous measurement of these outcomes and the process-metrics that drive them. For each individual project, the project leadership team will appoint individuals who will be responsible for the creation and continuous improvement of the multi-disciplinary care pathways that support the delivery of the project. These individuals will have defined accountability for the patient outcomes linked to the project, as well as the responsibility for communicating performance (improvement) against these outcomes throughout the life of the project. In order to achieve this, they will be part of the Forestland IT Transformation Group and specifically the data & analytics work stream (through which they will create the performance dashboards they will use for monitoring and communicating project-specific performance throughout the network). These project-specific performance monitoring leads will engage clinical specialties relevant to their projects through the professional peer groups described above. The Forestland PPS PMO will be responsible for consolidating all performance reporting metrics and measures – including the project-specific performance dashboards described above, and the DSRIP outcome measures – and reporting the most critical or high-risk metrics up to the Clinical Quality Committee and the PPS Board. The project leadership teams will be responsible for driving the sharing of best practice and performance information, through the project-focused breakthrough series and the annual learning collaboratives (described above).
Community engagement
Please describe your PPS's planned approach for driving community involvement in the DSRIP projects, how you will contract with CBOs for these projects, how community engagement will contribute to the success of the projects, and any risks associated with this.
Forestland PPS’s approach to driving community involvement in its projects begins from the top of its governance structure with the Community Initiatives Committee, a group made of community leaders with a direct line of communication to the PPS’s executive team. The Forestland Soup Kitchens (FSK) has been an active member of our PAC since August, 2014, and will be participating on our Population Health Management Sub-Committee. We have been in discussions with 4 other prominent CBOs about the DSRIP program, and expect to execute provider contracts with at least 5 organizations in total. The Forestland PPS PMO will be responsible for directing the input of specific community-based organizations in the development and delivery of specific projects – for example, we intend to involve Forestland Recovery in the delivery of our 3.a.i project and the Forestland Visiting Nurse Service will participate in several of our projects. The exact role of CBOs in project delivery will vary from project to project. However, in each project, the role of CBOs will center around the engagement of the target patient population. In the same vein, CBOs will also play a central role in some of the cross-cutting initiatives that support our project implementation – especially the drive to engage attributed members from culturally and linguistically isolated communities in Qualifying Entities. Whilst we do not envisage engaging in a provider contract with Patient Voices, collaborating with them around patient and community education is a central part of our strategy for improving the health literacy of our community and delivering Project 2.d.i.

## 2.a.i
2.a.i - Create an Integrated Delivery System focused on Evidence Based Medicine and Population Health Management
1. Measurable milestones and implementation risks
Sub-section 1. Major risks to implementation and mitigation strategies
Please describe what the major risks are for this project, as well as the actions that you plan to take to mitigate them.
[Note: The following text is an example of some of the many potential risks and mitigation strategies that could apply to this project and is meant to serve as an example. Specific risks as well as strategies may vary per PPS.] In Forestland’s provider community there has traditionally been a significant clinical and operational independence among providers, particularly in the primary care sector. This is the very fragmentation that led us to select project 2.a.i in the first place. The buy-in of staff at all levels – from the front line to the board – to the delivery model changes created by the DSRIP projects will therefore be crucial. The first step in mitigating this risk will be to develop a shared vision for the Forestland PPS, and to articulate the front line behaviors and practices that will be necessary to support this (multi-disciplinary decision making, pro-active focus on wellbeing and prevention, open data sharing). One of our methods of achieving this will be by using the MIX to post updates visible to all about our PPS’s progress, and to collect input from all participants. Following this, it will be easier to build support for the implementation of shared technical infrastructure and shared training, recruitment and redeployment. To track this risk, we need to monitor that all providers are engaged in project 2.a.i. The performance of the IDS Workgroup will be measured by the number of provider and/or practice sites that are actively participating in this project. The indicators that will define ‘active’ will include: (1) the use of patient registries; (2) involvement in coordinated care management (e.g. multidisciplinary team care planning); and the use of an (3) EHR with MU certification and connection to the SHIN-NY/QE. Monitoring the level of involvement throughout the network will be a key tool in monitoring and managing the risks created by a fragmented provider network. Another risk to the successful implementation of this project is our current inability to share clinical data between providers with current EMRs. To inform our DSRIP Project Plan Application, we reviewed the IT infrastructure in place throughout the network, with specific reference to our partners’ capabilities to share data. The gaps identified through this exercise represent a clear risk to this project. The upgrading of existing systems and integration of systems throughout the network – undertaken by the Forestland PPS IT Transformation Group and described in the IT Systems & Processes section – is our primary means of mitigating this risk. This upgrade and integration work will be one of the cross-cutting initiatives monitored at the PMO level. Additionally, we plan to encourage RHIO participation across the PPS to increase and improve connectivity.
Sub-section 2. Project Implementation Speed (for Project 2.a.i. only)
For Project 2.a.i, which involves all providers in a PPS’s network, setting out progress per provider would be overly onerous. For this project, PPSs will therefore be required to set out in the table below a work plan that sets out the (non-provider-specific) steps that underpin each of the PPS-wide project requirements.
Project 2.a.i
Project Requirements/sub-steps | Target Completion Date
1. All PPS providers must be included in the Integrated Delivery System. The IDS should include all medical, behavioral, post-acute, long-term care, and community-based service providers within the PPS network; additionally, the IDS structure must include payers and social service organizations, as necessary, to support its strategy.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
2. Utilize partnering HH and ACO population health management systems and capabilities to implement the strategy towards evolving into an IDS.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
3. Ensure patients receive appropriate health care and community support, including medical and behavioral health, post-acute care, long term care and public health services.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
4. Ensure that all PPS safety net providers are actively sharing EHR systems with local health information exchange/RHIO/SHIN-NY and sharing health information among clinical partners, including direct exchange (secure messaging), alerts and patient record look up, by the end of Demonstration Year (DY) 3.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
5. Ensure that EHR systems used by participating safety net providers must meet Meaningful Use and PCMH Level 3 standards by the end of Demonstration Year (DY) 3.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
6. Perform population health management by actively using EHRs and other IT platforms, including use of targeted patient registries, for all participating safety net providers.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
7. Achieve 2014 Level 3 PCMH primary care certification for all participating PCPs, expand access to primary care providers, and meet EHR Meaningful Use standards by the end of Demonstration Year (DY) 3.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
8. Contract with Medicaid Managed Care Organizations and other payers, as appropriate, as an integrated system and establish value-based payment arrangements.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
9. Establish monthly meetings with Medicaid MCOs to discuss utilization trends, performance issues, and payment reform.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
10. Re-enforce the transition towards value-based payment reform by aligning provider compensation to patient outcomes.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]
11. Engage patients in the integrated delivery system through outreach and navigation activities, leveraging community health workers, peers, and culturally competent community-based organizations, as appropriate.
Step 1…
Step 2…
[Please add additional steps based on your plan and timeline]

## 2.a.iv
2.a.iv Create a Medical Village Using Existing Hospital Infrastructure
1. Measurable milestones and implementation risks
Sub-section 1. Major risks to implementation and mitigation strategies
Please describe what the major risks are for this project, as well as the actions you plan to take to mitigate them.
[Note: The following text is an example of some of the many potential risks and mitigation strategies that could apply to this project and is meant to serve as an example. Specific risks as well as strategies may vary per PPS.] The major risk to implementing this project is the potential delay in freeing up the existing hospital capacity designated to be the site of the first Medical Village. The first Medical Village is planned to be built in Building C of Forestland Health Hospital - currently used to provide additional outpatient capacity at peak times when the facilities of Building B prove insufficient. Reducing the hospital’s need for Building C depends in part on the delivery of more coordinated, multi-disciplinary care across the network, thereby reducing the activity levels at Forestland Health Hospital. There will also be a specific decision, led by the Clinical Quality Committee, about which outpatient services are appropriately provided in Building C and how and where they will transition. However, these are relatively long-term impact, and this first Medical Village is planned to be completed and operational by the second quarter of Demonstration Year 2. In order to mitigate this risk, the construction and renovation required to create the medical village will begin in the East Wing of Building C only (approximately 60% of the total sq. footage), allowing for some of Building C’s capacity (i.e. the West Wing) to continue to be used during DY1, giving the hospital some time to adjust its needed capacity. Another risk that could hamper project 2.a.iv is the security concerns that surround the site. In the past, PCPs have moved their practices away from the Forestland Health Hospital area due to the notably high rate of gun violence and crime in the immediate area. Subsequently, medical services are sparse in the area, which is one of the reasons this site was chosen as a likely high-impact site for a medical village. These security concerns could jeopardize our plans for recruitment and redeployment of staff to the medical village site and could hamper our ability to direct patients to the medical village. To mitigate this risk we will: (a) work with two local CBOs that have experience of working to improve the safety of local neighborhoods; (b) develop green space around the clinic using adjacent deserted lots, including the former Pinetree Rubber Plant and (c) develop and implement a specific security plan in advance of opening the Medical Village. The two CBOs we have engaged with (‘Take Back Birchwood’ and ‘Safer Sprucefield’) have managed previous projects over the last five years to engage local communities in improving the safety of their own neighborhoods. Both projects have seen significant drops in crime rates. Our initial priorities for our dedicated security strategy include secure parking facilities and public transport.
Sub-section 2. Project Implementation Speed
Please specify how many providers will have met all of the project requirements (as set out in the Project Plan Application) per quarter. PPSs will be required to provide a progress report on this in each quarterly report and submit evidence of their progress to the Independent Assessor. The PPS’s performance against these targets will drive the ‘Project Implementation Speed Achievement Value’ for each payment period. Some project requirements are provider type-specific. A list of those project requirements that are provider type-specific will be published in due course. Your count of providers meeting 100% of project requirements per quarter should be non-cumulative - i.e. each cell represents the number of providers meeting 100% of the project requirements in that quarter.
Project Implementation Speed table
| Total # providers committed (as per project plan application) | No. of providers per category meeting 100% of project requirements per quarter
|  | DY1, Q2 | DY1, Q3 | DY1, Q4 | DY2, Q1 | DY2, Q2 | DY2, Q3 | DY2, Q4 | DY3, Q1 | DY3, Q2 | DY3, Q3 | DY3, Q4 | DY4, Q1 | DY4, Q2 | DY4, Q3 | DY4, Q4
Number of Medical Villages meeting all project requirements
Table 1
Sub-section 3. Patient engagement speed
In the Patient Engagement Speed section, PPSs will describe the ramp-up of their implementation in a greater level of detail than was required in the Application. In the table below, you should set out the number of patients that will have become ‘actively engaged’ by each quarter (or the number engaged in each quarter, depending on the counting methodology applied to that project). These detailed numbers must, of course, be in line with the half-yearly numbers that the PPS committed to in the Application. Your progress against these patient engagement speed commitments will be linked to a Domain 1 Process Payment.
Patient speed of implementation table
Expected # of actively engaged patients (total, as per project plan application) | [PPS TO ENTER NUMBER HERE]
| DY1, Q2 | DY1, Q3 | DY1, Q4 | DY2, Q1 | DY2, Q2 | DY2, Q3 | DY2, Q4 | DY3, Q1 | DY3, Q2 | DY3, Q3 | DY3, Q4 | DY4, Q1 | DY4, Q2 | DY4, Q3 | DY4, Q4
Patients Engaged

## 3.a.i
3.a.i Integration of Primary Care and Behavioral Health Services
IMPORTANT: Please select which model(s) you will pursue for this project by highlighting the cell(s) of the corresponding model(s) in YELLOW | [9 empty] | Model 1 (PCMH) | Model 2 (BH) | Model 3 (IMPACT)
1. Measurable milestones and implementation risks
Sub-section 1. Major risks to implementation and mitigation strategies
Please describe what the major risks are for this project, as well as the actions you plan to take to mitigate them.
[Note: The following text is an example of some of the many potential risks and mitigation strategies that could apply to this project and is meant to serve as an example. Specific risks as well as strategies may vary per PPS.] The first risk to this project’s successful implementation is the variation in approaches between primary care and behavioral health services in terms of assessment protocols, treatment pathways and referrals, and culture. Forestland PPS is undertaking all three models of this project, which has the potential to split the focus of the project leadership team. To mitigate this risk, careful attention needs to be placed on team development. For each pairing of primary and behavioral care providers, a program of intermittent job shadowing will be implemented to allow individual practitioners to understand each other’s roles. This will support the development of a joint education program, including learning collaboratives focused on developing a shared culture. This shared program of continuing education will also focus on sharing clinical understanding – such as physicians undergoing an in-service training on depression and medication management, or behavioral health specialists undergoing a course on the management of diabetes. This program directly ties into the training programs being developed in the clinical integration workstream. Another risk to the project is the existing regulatory and financing framework. As we await review and formal notice of our regulatory waiver requests, Forestland is cognizant of existing licensure and financing barriers, such as: separate collection windows and waiting rooms; limits on billing for clinical social work settings in Article 28s (unless an FQHC or for youth and postpartum women); per-patient caps on frequency of health physical codes in Article 31s; limited reimbursement for non-licensed staff such as peers and community health workers; and no reimbursement for intra-service care coordination services. While Forestland PPS will strive to develop value-based payment models for its integrated health services, the near-term fiscal sustainability of community-based practices is limited under a fee-for-service model (even when the payor is managed care), and we will closely monitor the financial viability of our community-based partners as the projects begin. The prevailing attitudes, judgments, expectations, and stigma towards behavioral health services, held by patients and their support circles, represents another risk to the successful implementation of this project. There is a risk that existing patients of primary care physicians could adversely react to the explicit introduction of behavioral health specialists and their patients into the primary care setting, irrespective of the existing significant behavioral health caseload of primary care physicians. To mitigate this potential risk the project leadership team will create a patient education and engagement plan on basic mental health and substance use issues, designed to address stigma around these services. Additionally, Forestland will pay special attention to workflow and patient engagement strategies so as to normalize the introduction of the new specialty [e.g., medical assistants asking about behavioral health symptoms such as sadness or sleeplessness at the same time as taking of blood pressure; behavioralists being introduced as “my colleague who specialize in stress management” ; and behavioral and medical staff sharing the same work space].
Sub-section 2. Project Implementation Speed
Please specify how many providers will have met all of the project requirements (as set out in the Project Plan Application) per quarter. PPSs will be required to provide a progress report on this in each quarterly report and submit evidence of their progress to the Independent Assessor. The PPS’s performance against these targets will drive the ‘Project Implementation Speed Achievement Value’ for each payment period. Some project requirements are provider type-specific. A list of those project requirements that are provider type-specific will be published in due course. Your count of providers meeting 100% of project requirements per quarter should be non-cumulative - i.e. each cell represents the number of providers meeting 100% of the project requirements in that quarter.
Project Implementation Speed table
|  |  | Total # providers committed (as per project plan application) | No. of providers per category meeting 100% of project requirements per quarter
|  |  |  | DY1, Q2 | DY1, Q3 | DY1, Q4 | DY2, Q1 | DY2, Q2 | DY2, Q3 | DY2, Q4 | DY3, Q1 | DY3, Q2 | DY3, Q3 | DY3, Q4 | DY4, Q1 | DY4, Q2 | DY4, Q3 | DY4, Q4
Primary Care Physicians | Primary Care Physicians | Primary Care Physicians
Non-PCP Practitioners | Non-PCP Practitioners | Non-PCP Practitioners
Clinics | Clinics | Clinics
Behavioral Health | Behavioral Health | Behavioral Health
Substance Abuse | Substance Abuse | Substance Abuse
Community Based Organizations | Community Based Organizations | Community Based Organizations
All Other | All Other | All Other
All Committed Providers
Table 1
Sub-section 3. Patient engagement speed
In the Patient Engagement Speed section, PPSs will describe the ramp-up of their implementation in a greater level of detail than was required in the Application. In the table below, you should set out the number of patients that will have become ‘actively engaged’ by each quarter (or the number engaged in each quarter, depending on the counting methodology applied to that project). These detailed numbers must, of course, be in line with the half-yearly numbers that the PPS committed to in the Application. Your progress against these patient engagement speed commitments will be linked to a Domain 1 Process Payment.
Patient speed of implementation table
Expected # of actively engaged patients (total, as per project plan application) |  |  | [PPS TO ENTER NUMBER HERE]
|  |  | DY1, Q2 | DY1, Q3 | DY1, Q4 | DY2, Q1 | DY2, Q2 | DY2, Q3 | DY2, Q4 | DY3, Q1 | DY3, Q2 | DY3, Q3 | DY3, Q4 | DY4, Q1 | DY4, Q2 | DY4, Q3 | DY4, Q4
Patients Engaged

## 4.a.iii
4.a.iii Strengthen Mental Health and Substance Abuse Infrastructure across Systems (Focus Area 3)
1. Measurable milestones and implementation risks
Major risks to implementation and mitigation strategies
Please describe what the major risks are for this project, as well as the actions you plan to take to mitigate these risks.
[Note: The following text is an example of some of the many potential risks and mitigation strategies that could apply to this project and is meant to serve as an example. Specific risks as well as strategies may vary per PPS.] One high-level risk that affects this project is where the project’s focus and targeted allocation of resources become diluted due to: (a) the cultural, linguistic and geographic diversity of the populations we are seeking to target; and (b) the sheer number of social factors that drive mental health and substance abuse problems for our attributed population. Our CNA identified low incomes, employment, housing and safety as key drivers of poor mental health and substance abuse in Forestland. Addressing this wide range of factors creates a scope for this project that is very broad, and can potentially threaten project momentum. In order to address this, the project leadership team for this project will establish a CBO Council, designed to engage local community-based organizations in the delivery of this project specifically. This Council has not yet been established but we have already signed up the Forestland Alliance on Mental Illness (FAMI), the Forestland Department of Social Services, the Forestland Welcoming Center and the Arbor Housing Trust and we intend to target CBOs with specific relationships with culturally and linguistically isolated communities. Another challenge we face in implementing and monitoring this project will be the identification of supplementary short-term outcome measures, and gathering supporting data sets that will allow us to monitor improvements to population health in terms of mental health and substance abuse over a shorter timeframe. While this task may be difficult, we determined from our CNA that supplementing the few existing DSRIP outcome measures for Goal 3 with additional metrics would provide more targeted support for our PPS’s at-risk population. We are negotiating a partnership with the Forestland Office of Health and Mental Hygiene, the core focus of which will be to define and monitor appropriate outcome measures as well as to collaborate on behavioral health needs and resources. This partnership will allow us to tap into FOHMH’s relationships with law enforcement agencies and housing agencies at a local government level. Working with these agencies should allow us to track some of the most important outcomes of improved mental health and substance abuse infrastructure. Another risk to the successful implementation of project 4.a.iii is the lack of patient-level data about the individuals within our attributed population who have mental, emotional and behavioral health and substance abuse issues. This is particularly – but not solely – true for our large homeless population and the populations of recent immigrants, who are often culturally or linguistically isolated and make limited use of available health services. This lack of information will hamper our efforts to scale this project appropriately and target the right individuals. It will also compound the challenge outlined above regarding outcome measures. Our CBO Council will be one vital tool in contacting and engaging isolated populations. In addition, the project leadership teams for our Domain 4 projects will have a specific mandate to engage with local businesses, churches and other faith groups and commercial and other managed care organizations. Given the overlap between culturally and linguistically isolated populations, the individuals who are not accessing health services appropriately, and the individuals with mental, emotional and behavioral health and substance abuse issues, we have taken the decision to establish a joint project leadership team for this project and Project 2.d.i. (patient activation activities targeting the uninsured and low/non-utilizing Medicaid populations). We believe this approach will also help to mitigate the risks described above.

## Values (hidden)
Not started
In Progress, Delayed | DY1, Q2
In Progress, On Track | DY1, Q3
Complete | DY1, Q4
DY2, Q1
DY2, Q2
DY2, Q3
DY2, Q4
DY3, Q1
DY3, Q2
DY3, Q3
DY3, Q4
DY4, Q1
DY4, Q2
DY4, Q3
DY4, Q4
DY5, Q1
DY5, Q2
DY5, Q3
DY5, Q4